## Projects
S.No | Project Name | Size | Status | Location | Folder Link | Years | Remarks
1 | BBCL Midland | 50 | Completed | Navalur |  | 2022
2 | Zebronics | 9.9 | Completed | Rayapettai |  | 2023
3 | Dr Sivabalan |  | Completed | Nolambur |  | 2024
4 | Indus Allaiance | 2 | Completed | Anna Nagar |  | 2024
5 | Mr Srinivasan | 9.8 | Completed | Panaiyur |  | 2024
6 | Ramaniyam Subham | 2.2 | Completed | Besant Nagar |  | 2024
7 | Ramaniyam Sasta | 3.3 | Completed | Nungambakkam |  | 2024
8 | Ramaniya Syndicate | 5.4 | Completed | Adyar |  | 2024
9 | DRA Homes | 25 | Completed | Navalur |  | 2024
10 | Mr Rajesh | 10 | Completed | Navalur |  | 2024
11 | Dr Sridhar | 7 | Completed | Thambaram |  | 2024
12 | Mr Varun | 4.32 | Completed | Besant Nagar |  | 2024
13 | Mr Muthu | 10 | Completed | ECR |  | 2024
14 | Lancor TCP Altura | 20 | Completed | Solinganallur |  | 2024
15 | Sribalaji Lancor | 4.69 | Completed | Anna Nagar |  | 2024
16 | L&T | 7.7 | Completed | RA Puram |  | 2024
17 | Navins Hanging Garden | 25.85 | Completed | Valasaravakkam |  | 2024
18 | Ramaniyam Senate | 6.6 | Completed | K K Nagar |  | 2024
19 | Ramaniyam Kalpataru | 3.2 | Completed | Ashok Nagar |  | 2024
20 | SSBPL KS Avanue | 4 | Completed | Mylapore |  | 2024
21 | Chettinad Hospital | 60 | Completed | Mahabalipuram |  | 2024
22 | Hari Shree Senior School | 81 | Completed | RA Puram |  | 2024
23 | Hari Shree Junior School | 9.9 | Completed | RA Puram |  | 2024
24 | Ceebros boulevard | 82 | Completed | Thuraipakkam |  | 2024
25 | Radiance Flourish | 240 | Completed | Thiruvotriyur |  | 2024
26 | Enexio Fill Factory | 95.6 | Completed | Puduvayal |  | 2024
27 | Abirami Eng Cons & Co | 20 | Meter Client Scope | Shenoy Nagar |  | 2024
28 | Mr Karthikeyan / TVS Hamlet | 6 | Completed | Karapakkam |  | 2024
29 | RWD Grand Corridor | 75 | Completed | Poonamalle |  | 2024
30 | Jains Anarghya | 19 | Meter Client Scope | Pallikaranai |  | 2024
31 | Jains Aadheeswar | 42 | Meter Client Scope | Manapakkam |  | 2024
32 | Jains Advaya | 64 | Holding from Shiroi | Kouvur |  | 2024
33 | Mr Rathinam | 5 | Completed | Adyar |  | 2024
34 | Mr Anandan | 4 | Completed | Nolambur |  | 2024
35 | Ramaniyam Summit | 3.3 | Completed | Besant Nagar |  | 2024
36 | Ramaniyam Trinity | 5.5 | Completed | Thiruvanmiyur |  | 2024
37 | Mr Kannaiyan | 2.2 | Completed | Nanganallur |  | 2024
38 | Mr AM Raja | 3.4 | Completed | Garpagam Garden |  | 2024
39 | Mr Krishnamurthy | 2 | Completed | Thiruvanmiyur |  | 2024
40 | GRN Kuyili | 2 | Completed | T Nagar |  | 2024
41 | Geeyam Meenakshi Illam | 4 | Completed | Mandaveli |  | 2024
42 | GK Shetty tulive Bellevue | 44 | Completed | Valasaravakkam |  | 2024
43 | Mr Swaminathan | 3.2 | Completed | Thambaram |  | 2024
44 | Prestige Hill Crest | 135 | Waiting for Net Meter | Ooty | https://drive.google.com/drive/folders/14vxMc1RqlBTu-URNstBZ-KWqTE387sv5 | 2024 | Nil
45 | Sheela Green | 13.5 | Completed | Anna Nagar |  | 2024
46 | Navins Starwood | 36 | Completed | Vengaivasal |  | 2024
47 | Shree Vrikshah homes | 9.9 | Completed | Alwarpet |  | 2024
48 | Legendry Builders | 9.9 | Completed | Gopalapuram |  | 2024
49 | Mr Srinivasan L&T | 5 | Completed | Korratur |  | 2024
50 | Khurinji's Iris | 3 | Completed | Thiruvanmiyur |  | 2024
51 | Hindu School Payalwar Street | 110 | Completed | Triplicane |  | 2024
52 | Adroit Prosper | 10 | Completed | Thazhambur |  | 2024
53 | RCC e Constrcution | 20 | Completed | Mangadu |  | 2024
54 | Mr Saravana Bhava | 2 | Completed | Perungalathur |  | 2024
55 | Mr Srinivasan Madipakkam | 2 | Completed | Madipakkam |  | 2024
56 | Ramaniyam Parampara | 3.3 | Completed | Mylapore |  | 2024
57 | Mr Ravish | 3.5 | Completed | Madipakkam |  | 2024
58 | GRN Shree Nivas | 2 | Completed | Nungambakkam |  | 2024
59 | GRN Mangaladev | 2 | Completed | Anna Nagar |  | 2024
60 | Mr Bharath | 5 | Completed | Besant Nagar |  | 2024
61 | Mr.Anilkumar Mehta - Home | 8.8 | Completed | Coimbatore |  | 2024
62 | Opus 96 | 5.9 | Completed | Tambaram |  | 2024
63 | BEEL | 3.3 | Completed | Nandanam |  | 2024
64 | Ramaniyam Padhuka | 2.7 | Completed | Mylapore |  | 2024
65 | DMS | 29 | Holding from client | Vanagaram |  | 2024
66 | CM Constrcution | 3.3 | Completed | Nerkundram |  | 2024
67 | Mr Muralidharan | 3.3 | Completed | Chithalapakkam |  | 2024
68 | Mr Devadoss | 7 | Completed | Pallikaranai |  | 2024
69 | Mr Seshadri | 4 | Completed | West Mambalam |  | 2024
70 | SLNC | 13.5 | Completed | Madurai |  | 2024
71 | Mr Lakshmanan | 3.3 | Completed | Nanganallur |  | 2024
72 | SSBPL KP Puram | 8 | Completed | Kesavadasapuram |  | 2024
73 | Mr Chakrapani | 4.4 | Completed | West Mambalam |  | 2024
74 | Lancor Infinys | 20 | Completed | Keelkatalai |  | 2024
75 | Ramaniyam Adhri | 2.2 | Completed | Anna Nagar |  | 2024
76 | Mr MV Srinivasan | 13.2 | Completed | T Nagar |  | 2024
77 | Mr Kesav Anand | 2.2 | Completed | Moovarasanpet |  | 2024
78 | Khurinji's Acanthus | 5 | Completed | Madipakkam |  | 2024
79 | Shree Niketan | 9 | Completed | Anna Nagar |  | 2024
80 | Geeyam Nandhini | 4 | Completed | St Mary's Road |  | 2024
81 | 4 Bricks | 5 | Completed | Adyar |  | 2024
82 | GRN Bakhavachalam | 2 | Completed | Bakthavatchalam |  | 2024
83 | GRN CP Ramasamy | 2 | Completed | CP Ramaswamy Street |  | 2024
84 | Mr Arangarajan | 5 | Completed | Thiruvanmiyur |  | 2024
85 | Mr C Kumar | 3.2 | Completed | Madipakkam |  | 2024
86 | Mr Sangeetha | 5.5 | Completed | Manapakkam |  | 2024
87 | Navins Vyakarana | 5 | Completed | T Nagar |  | 2024
88 | Vgk Saiharithik | 5 | Completed | Thambaram |  | 2024
89 | Mr Vigneswaran | 3.3 | Completed | Madipakkam |  | 2024
90 | Vinayaga Infratech | 5 | Completed | Pallavaram |  | 2024
91 | Mr Ramkumar | 3.3 | Completed | Karapakkam |  | 2024
92 | Ms. Sridevi | 3.3 | Completed | Karapakkam |  | 2024
93 | Mr Lakshman Raj | 3.3 | Completed | Karapakkam |  | 2024
94 | Mr Balaji | 3.3 | Completed | Karapakkam |  | 2024
95 | Mr Aatish | 3.3 | Completed | Karapakkam |  | 2024
96 | VGK Unity Kingdom | 10 | Completed | Karapakkam |  | 2024
97 | VGK Summer Garden | 20 | Completed |  |  | 2024
98 | MSM Unit II, Phase III | 250 | Completed | Coimbatore |  | 2024
99 | Ramaniyam Abinaya | 3.3 | Completed | Adyar |  | 2024
100 | Rite Choice | 2 | Completed | Ashok Nagar |  | 2024
101 | S&P Courtyard | 30 | On Progress | Ayanampakkam | https://drive.google.com/drive/folders/1-aaHi4sgjRn3B6JVbu6aRyJlQA6rsd5f | 2024 | Nil
102 | VP Jewellery | 5 | Completed | Chennai |  | 2024
103 | Mr Chandrasekar | 3 | Completed | Choolaimedu |  | 2024
104 | SSBPL NBR 2 | 4.4 | Completed | Thiruvamiyur |  | 2024
105 | Lancor Hiranmayi | 5 | Completed | T Nagar |  | 2024
106 | Lancor Sahana | 5 | Completed | T Nagar |  | 2024
107 | Lancor Ratirupa | 5 | Meter Client Scope | T Nagar |  | 2024
108 | Lancor Homeleigh | 5 | Completed | Nungampakkam |  | 2024
109 | Arihanth Nahar | 10 | Completed | Mettupalaiyam |  | 2024
110 | Mr Ramaswamy | 3.3 | Completed | Anna Nagar |  | 2024
111 | Mr Venkateswaran RTO | 7 | Completed | Nolambur |  | 2024
112 | SSBPL West Mambalam | 3.3 | Completed | West Mambalam |  | 2024
113 | Kalakchetra | 10 | Waiting for Net Meter | Adyar | https://drive.google.com/drive/folders/1iAruyKz0k1EhRHFm2rwI4IOZzW-nOXeN | 2024 | Nil
114 | Mr Venkatraman | 9 | Completed | Maduravoyal |  | 2024
115 | Ramaniyam Shyamala | 3.3 | Completed | RK Nagar |  | 2024
116 | DRA Urbania | 67 | Completed | Avadi |  | 2024
117 | Mr.Sriram Pallikaranai | 4 | Completed | Pallikaranai |  | 2024
118 | Ramaniyam Sri Vaikuntam | 3.3 | Completed | Ram Nagar |  | 2024
119 | Newry Astor | 10 | Completed | Avadi |  | 2024
120 | Vaf def Aero Systems | 528 | Completed | Coimbatore |  | 2024
121 | Mr Parasuraman | 5 | Completed | Korattur |  | 2024
122 | Mr Palanivelan | 3.3 | Completed | Kodampakkam |  | 2024
123 | SSBPL SPRING SEASON | 3.3 | Completed | Nungampakkam |  | 2024
124 | Luxebuilt Homes Pvt ltd | 3.3 | Completed | Aibea Nagar |  | 2024
125 | Lancor Lumina H2 | 20 | Meter Client Scope | Guduvanchery |  | 2024
126 | Felix Johnson | 7.5 | Completed | Madampakkam |  | 2024
127 | Mr Elumalai | 3.3 | Completed | Pampal |  | 2024
128 | Log on infra pvt ltd (NDR) | 22.5 | Completed | T Nagar |  | 2024
129 | M/S Ramya | 10 | Completed | Olympia Panache |  | 2024
130 | Mr Davidson | 8.7 | Completed | Selaiyur |  | 2024
131 | Navins Sankalpa | 8 | Completed | Adyar |  | 2024
132 | Sri Ganapathy Ashram | 14 | Completed | Velachery |  | 2024
133 | Jains Aura | 3 | Completed | Thiruvallur |  | 2024
134 | Mr Manokaran | 3 | Completed | Nungampakkam |  | 2025
135 | Mr Vijay Sabapathy | 10 | Completed | Madipakkam |  | 2024
136 | Sri Ganapathy Ashram, Phase II | 9.9 | Completed | Velachery |  | 2024
137 | Mr Venkatesh | 3.3 | Completed | Karapakkam |  | 2025
138 | Mr Koildhass | 5 | Completed | Selaiyur |  | 2025
139 | Ramaniyam Bharadwaj | 4.4 | Completed | Mandavali |  | 2025
140 | M/s Latha ganesh | 5 | Completed | Besant Nagar |  | 2025
141 | Ramaniyam Nagas | 3.3 | Completed | Adyar |  | 2025
142 | Ramaniyam tulsi | 5 | Completed | Besant Nagar |  | 2025
143 | Ramaniyam Anugraha | 8.8 | Completed | Ashok Nagar |  | 2025
144 | Ramaniyam Ocean dew Block 4 | 8.8 | Completed | Pallikaranai |  | 2025
145 | Ramaniyam Ocean dew Block 5 | 8.8 | Completed | Pallikaranai |  | 2025
146 | Ramaniyam Vedha | 3.3 | Completed | Adyar |  | 2025
147 | Town & Country Project | 0 | Completed | Sriperumpudhur |  | 2025
148 | Nithya Akshayam | 5.5 | Completed | Nanganallur |  | 2025
149 | Mr Vishnu Vijay | 3.3 | Completed | Poonamalle |  | 2025
150 | M/s Srividya Srikanth | 3.3 | Completed | West Mambalam |  | 2025
151 | Mr Subramanian | 6.6 | Completed | Koturpuram | https://drive.google.com/drive/folders/18ULAJaInD_x6cJ0ekns5fWCTk9Br1F2j | 2025 | Nil
152 | Mr Babu Govindrajan | 3.3 | Completed | Nungampakkam |  | 2025
153 | Mr Saravanan | 5 | Completed | Adyar |  | 2025
154 | Mr Sairam | 5 | Completed | Anna Nagar |  | 2025
155 | Mr Sankaranarayanan | 3.3 | Completed | Madampakkam |  | 2025
156 | DRA Skylanties | 19 | On Progress | Semancheri | https://drive.google.com/drive/folders/1N6HBufOVOjvrM2avvUMb5HJdMdmtAsfD | 2025 | yet to deliver the materials
157 | Mr Venkatesh | 3.3 | Completed | velachery |  | 2025
158 | Geeyam Skandha | 4.4 | Completed | Mandavelipakkam |  | 2025
159 | Mr Chandran | 4.4 | Completed | Navalur |  | 2025
160 | Mr Jeyaseelan | 3.3 | Completed | Kaspapuram |  | 2025
161 | Krishna Ekta | 3.3 | Holding from client | West Mambalam | https://drive.google.com/drive/folders/1oABsdjuJ0HyXA6uemXQlZUP7pN9-Na5X | 2025 | Nil
162 | Mr Sriram | 6 | Completed | Nungampakkam |  | 2025
163 | Mr Venkateshperumal | 3.3 | Completed | Chitlapakkam |  | 2025
164 | Mr. Ramesh Babu | 3.3 | Completed | Karapakkam |  | 2025
165 | DRA Optima | 40 | Completed | Avadi |  | 2025
166 | Mr Sanjay | 9.9 | Completed | Kilpauk |  | 2025
167 | Mr Ginu Mathew | 3.3 | Completed | Karapakkam |  | 2025
168 | Dr Ramesh | 5 | Completed | Teynampet |  | 2025
169 | Ranamaniyam Saranagati | 3.3 | Completed | Ashok Nagar |  | 2025
170 | Pacifica Aurum | 3.3 | Completed | Padur |  | 2025
171 | Mr Prabakaran | 3.3 | Completed | Abiramapuram |  | 2025
172 | RCC e Constrcution 2 | 20 | Meter Client Scope | Mangadu |  | 2025
173 | GRN Chakarabani street | 2.2 | Completed | West Mambalam |  | 2025
174 | Mr Siva Elango | 5 | Completed | Virugampakkam |  | 2025
175 | Shoba Silks Pvt Ltd | 100 | Waiting for Net Meter | Karapakkam |  | 2025
176 | Green Crest | 9.7 | Completed | Thirumangalam |  | 2025
177 | Mr Shanmugam | 5.5 | Completed | Saligramam |  | 2025
178 | Krishnaveni | 9.3 | Completed | Thindivanam |  | 2025
179 | Jyothiswari | 2.2 | Completed | Thindivanam |  | 2025
180 | Mr Sivasankar | 2.2 | Completed | Anna Nagar |  | 2025
181 | Lancor Lumina ABC | 20.5 | Holding from client | Guduvanchery | https://drive.google.com/drive/folders/1NcXI4zV9hFa6MDweUTVqZ4N1nhUqxJoW | 2025 | Nil
182 | Sri krishna Sweets | 20 | Waiting for Net Meter | Coimbatore |  | 2025
183 | Mahameru | 10 | Waiting for Net Meter | Thiruvanmiyur | https://drive.google.com/drive/folders/1q01x66w1_XNAtaL_wW4RtqI1xunJYK-b | 2025 | Nil
184 | Jains Seven 77 | 30 | Holding from client | Perungudi | https://drive.google.com/drive/folders/12q-BgaRbCF3KZWBCMuDBWSfgxB0cF6E7 | 2025 | Nil
185 | SPDPL Luz Avenue | 8 | Completed | Mylapore |  | 2025
186 | Jains Aadhidev | 30 | Holding from client | Manapakkam | https://drive.google.com/drive/folders/1Nzc9DRsU_Vq9A5If0O2Ajjq6aN6b_UCW | 2025 | Nil
187 | Mr Arjun Prasath | 9.7 | Completed | Mylapore |  | 2025
188 | Zeneto infra | 3.3 | Waiting for Net Meter | Velachery |  | 2025
189 | Mr Sridhar Rajan | 6 | Completed | Madipakkam |  | 2025
190 | Mr Rangachari | 8 | Completed | Ramapuram |  | 2025
191 | Mr.Sukumaran | 3.3 | Completed | Kottivakkam |  | 2025
192 | Ramaniyam Nivasam | 4.4 | Completed | Adyar |  | 2025
193 | Hindu School Adyar / Service | 50 | Completed | Adyar |  | 2025
194 | GRN Ambili Srinivas | 3.3 | Completed | T Nagar |  | 2025
195 | SPDPL Padmalaiya | 4.4 | Completed | Alwarpet |  | 2025
196 | Nirupa Properties | 2.2 | Completed | Madipakkam |  | 2025
197 | Mr.Karthikeyan / CM Constructions | 4.8 | Completed | Nolambur |  | 2025
198 | Sri krishna Sweets Factory | 100 | On Progress | Coimbatore | https://drive.google.com/drive/folders/13Rs28n7vZ_Q32Yko3XLJXCht1eD5pCNx | 2025 | Nil
199 | Mr Ravi / Tiruvannamalai | 10 | Completed | Thiruvannamalai |  | 2025
200 | Mr.Arunkumar | 3.3 | Completed | Medavakkam |  | 2025
201 | Rakshas Enterprises | 10 | Waiting for Net Meter | Coimbatore |  | 2025
202 | Mr.Anilkumar Mehta - Office | 10.5 | Completed | Coimbatore |  | 2025
203 | Mr.Rajan Babu | 6.6 | Completed | Neelankarai |  | 2025
204 | Ramaniyam Sankaram | 4.4 | Completed | RA Puram |  | 2025
205 | Mr Raja grn gopal street | 10 | Completed | West Mambalam |  | 2025 | Nil
206 | Mr.Kasinathan | 8.8 | Completed | Palavanthangal |  | 2025
207 | Newry Adora | 20 | Holding from client | Avadi | https://drive.google.com/drive/folders/1_HNJIoUBDK7XFLONbVlEMzFkN9Pz6m0u | 2025 | Nil
208 | Lancor Bagya | 5 | Holding from client | Besant Nagar | https://drive.google.com/drive/folders/1Y9yLWQW3rGmm5ZITWygsME9m4Xn7XdWi | 2025 | Nil
209 | Lancor Ananda | 5 | Waiting for Net Meter | Gopalapuram | https://drive.google.com/drive/folders/1ACnaJELmrcNmVxcxNpO32t-GaK_lIMAq | 2025 | Nil
210 | Mr Jeyakumar | 4.8 | Completed | Madampakkam |  | 2025
211 | Geeyam Suryakantham | 3.3 | Completed | Raja Annamalaipuram |  | 2025 | Nil
212 | Geeyam Prasang | 4.4 | Completed | Abiramapuram |  | 2025 | Nil
213 | Mr Saravanan 4 Bricks | 3.3 | Waiting for Net Meter | Adyar |  | 2025
214 | Mr Srinivasan Adyar | 6 | On Progress | Adyar | https://drive.google.com/drive/folders/12dTuol10rXJdtokKsWTPq8LAx93pX50u | 2025 | Nil
215 | Mr Nitin | 6 | Completed | Vepery |  | 2025 | Nil
216 | Khurinji's the Orchid | 5 | Completed | Adyar |  | 2025 | Nil
217 | Ramaniyam Rangavilasam | 3.3 | Completed | Nanganallur |  | 2025
218 | VM Builder | 5 | Completed | Egmore |  | 2025 | Nil
219 | Shankaran - Shree Viruksha | 8 | Waiting for Net Meter | Besant Nagar |  | 2025
220 | Ramaniyam Gayathri | 5.4 | Completed | Thiruvanmiyur | https://drive.google.com/drive/folders/19Dmq93qv-SoxcDylN_WImDVq-m-S-ku8 | 2025 | Nil
221 | Ramaniyam Manasa | 9.8 | Waiting for Net Meter | Anna Nagar |  | 2025
222 | Swarnalatha | 4.3 | Completed | Mugalivakkam |  | 2025
223 | Adroit Prosper D Block | 10 | Holding from client | Thalambur | https://drive.google.com/drive/folders/1-dds5p0THDcEX_3OKWAXR77GSOpax-sp | 2025 | Waiting for CC
224 | Mr Sundar | 5.5 | Completed | Perungudi |  | 2025 | Nil
225 | Accord Foundtaions | 30.42 | On Progress | Mylapore | https://drive.google.com/drive/folders/1TCcYwVwWz9AeKYjZDJp54RZ-3mahmk6K | 2025 | Nil
226 | Zirve Project | 30 | Yet to Start | Saligramam |  | 2025
227 | Ekana Cottage | 8 | Waiting for Net Meter | Alwarpet |  | 2025 | Nil
228 | Mr Aditya Baskar | 4.2 | Completed | Thuraipakkam |  | 2025
229 | Mr Manickam | 1.2 | Completed | Thuraipakkam |  | 2025
230 | M/s Geetha Kalyan | 1.8 | Completed | RA Puram |  | 2025 | Nil
231 | Syed Mubarak | 6.3 | Waiting for Net Meter | Manapakkam |  | 2025
232 | Mr Vasu rao | 4.2 | Completed | Teynampet |  | 2025 | Nil
233 | DRA Trinity | 35.2 | On Progress | Thuraipakkam | https://drive.google.com/drive/folders/1vH39fpF8BDgLH1Mrv_mZUPc2oDgFIjSZ | 2025 | Nil
234 | National School | 15 | Waiting for Net Meter | Mayiladuthurai |  | 2025
235 | Mr Sivasankar Home | 3 | Completed | Anna Nagar |  | 2025
236 | Chettinad Grinding Unit | 10 | Waiting for Net Meter | Vizag | https://drive.google.com/drive/folders/14SSmOv7B7K0XXgcIxOxoBfxTQ1L829Su | 2025 | Nil
237 | Mr Parasuraman 2 | 7.2 | On Progress | Anna Nagar | https://drive.google.com/drive/folders/1ONWUK-qHtIBRDCGvOIvgqkvZLkkqsnF3 | 2025 | Nil
238 | Alamelu & Arvind | 9.9 | Completed | Uthandi |  | 2025 | Nil
239 | Mr Solai Ayyar | 8.6 | Completed | Ramapuram |  | 2025 | Nil
240 | Ramaniyam Premasaraswathi | 6.6 | Waiting for Net Meter | Mylapore |  | 2025 | Nil
241 | Mr Pradip Jasiwal | 8.6 | Completed | Puraisaivakkam |  | 2025
242 | Mr Mithil & Karan | 16 | Waiting for Net Meter | Vellore |  | 2025
243 | Radiance Splendour | 161 | Completed | Coimbatore | https://drive.google.com/drive/folders/1P3t87ghU6qcpfXLVyE-PeSsV2foYqFOB | 2025 | Nil
244 | S&P The Address | 2.4 | Waiting for Net Meter | Mambakkam |  | 2026
245 | Ramaniyam Ashok Vihar | 7.7 | Waiting for Net Meter | Ashok Nagar |  | 2026
246 | Mr Deepak Raj | 3.3 | Completed | Ponniammanmedu | https://drive.google.com/drive/folders/1SbBusvO0oGc2TAhh8RiMe-cLJqOeEzwf | 2026 | Nil
247 | RCC Austrom Icon | 10 | Completed | Maraimalainagar | https://drive.google.com/drive/folders/1O2a5lCqX_56l2bEflL1X4v1YxrciMKoZ | 2026 | Nil
248 | Ramaniyam Akshayam | 5.5 | Waiting for Net Meter | K K Nagar | https://drive.google.com/drive/folders/15XFtwTskGMGciukbWpefNMr8xxkWG5G2 | 2026 | Nil
249 | Ramaniyam Radika | 4.4 | Waiting for Net Meter | Kilpauk | https://drive.google.com/drive/folders/1Om-ZBNXJZb-6qj4PX-0UaW856ZiyPouv | 2026 | Nil
250 | M/s Deepa Balaji | 3 | Completed | Adyar | https://drive.google.com/drive/folders/1YYC3KN1JGAbgcNAsGHF10DHPQuuiCF2- | 2026 | Nil
251 | Mr Pradheep Boopathy | 3 | Completed | Adyar | https://drive.google.com/drive/folders/1NT0YcwUZjP7waBc4nZD_ywLyMUix3ECy | 2026 | Nil
252 | Mr Murali | 4.8 | Completed | Pammal | https://drive.google.com/drive/folders/14GR6CVn7f2aa_iZv1E75WavytLGCJolp | 2026 | Nil
253 | Ramaniyam Lakshmi | 4.4 | On Progress | Adyar | https://drive.google.com/drive/folders/1zzM--JwuCTVcM7a8EOyAL-n_FK8dAv-K | 2026 | Nil
254 | Navins Starwood Towers Phase III | 36 | Yet to Start | Vengavasal | https://drive.google.com/drive/folders/1URIBqqHA-mZznmATdGmGNpH0Br0t8Z-2 | 2026 | to get Quote from sriram for structure
255 | Dra Downtown | 72 | Holding from client | Egmore | https://drive.google.com/drive/folders/1ZRmYlboeiXxtwCkJGC0698e0wyeHZOAi | 2026 | Waiting for CC
256 | M/s Jayanthi | 5 | Yet to Start | Besant Nagar | https://drive.google.com/drive/folders/1Um-epJUDhZcq0HWmyMTv0Zxvtnbiu4eu | 2026 | Waiting for panel
257 | Mr Swaminathan | 6 | Yet to Start | T Nagar | https://drive.google.com/drive/folders/10ukP0lT7gFNrI-YZiObMgufAseed1wo- | 2026 | Waiting for panel
258 | M/s Uma Maheshwari | 5 | Yet to Start | Kolathur | https://drive.google.com/drive/folders/1zCaKAQSAMH5n_8cuTQ1ZzPOf6bUX6paz | 2026 | Waiting for design and panel
259 | M/s V J Saraswathi | 3 | Yet to Start | Abiramapuram | https://drive.google.com/drive/folders/1W20Cfxofy-ij2nNzfk3nQPWg7ERaZBlg | 2026 | Nil
260 | Mr Sri Kumar | 11 | Waiting for Net Meter | Ashok Nagar | https://drive.google.com/drive/folders/1qMwG4QRWpf4oegGC8MOmUJGinpTeeYpy | 2026 | Nil
261 | BCPL Anusham | 5 | Yet to Start | Nanganallur | https://drive.google.com/drive/folders/1GA2LmK7BuG8-EydX2LQL4kDMEO21snZ5 | 2026 | Nil
262 | BCPL Anusham / Arjun Prasath | 7 | Yet to Start | Nanganallur | https://drive.google.com/drive/folders/12NipA59dsYn2IOMe0C0xVNetbfLp3J4M | 2026 | Nil
263 | BCPL Anusham / Dhandapani | 2.3 | Yet to Start | Nanganallur | https://drive.google.com/drive/folders/1C67HmuEHhmuyihELsv1QuY9rISoKKq2o | 2026 | Nil
264 | BCPL Anusham / Ramesh | 2.3 | Yet to Start | Nanganallur | https://drive.google.com/drive/folders/1NlLczFjk0yF-l1GnYCxFimlgzWYEkCst | 2026 | Nil
265 | BCPL Anusham / Sri Bala | 5 | Yet to Start | Nanganallur | https://drive.google.com/drive/folders/1I0lRQuYNO2igzJuR2EKnNSC7t-xPp92K | 2026 | Nil
266 | DRA Infinique | 18 | Yet to Start | Maduravoyal | https://drive.google.com/drive/folders/11ywfvFB3LeIIEY2hnFw3Bw3kPXNcj3Mt | 2026 | Nil

## Tasks
Project Name | Task Name | Assigned to | Status | Due date | Notes | Done by
Ramaniyam Nivasam | to deliver materials to site | Sathyaraj | Closed | 2025-12-06 05:30 | [ 03/12/2025 - Panels delivered to Site by Sathyaraj ] / [ 08/12/2025 - Structure delivered to site by Suresh from green field] | Suresh
Ramaniyam Sankaram | to deliver the panels & Str to site | Suresh | Closed | 2025-12-08 05:30 | [ 29/11/2025 - Site Visit & design confirmation got by Suresh ] / [ 3/12/2025 - Panels delivered to site by Sathyaraj ] / [ 08/12/2025 - Structure materials delivered to site by Suresh from green field ] | Suresh
Jains Aadheeswar | to start & complete the electrical work | Manivel | Closed | 2025-12-31 05:30 | Electrical work completed at site by contractor Sriram | Mohan
Newry Adora | to deliver the panels & Structure to site | Sathyaraj | Closed | 2025-12-05 05:30 | [ 28/11/2025 - Structure order Placed with green Field ] / [ 1/12/2025 - Panel Order Placed with Southern Power ] / [ 4/12/2025 - Co ordinated for both panel & structure deliver to site - both are ready to dispatch ] / [ 05/12/2025 - Panel & structure materials delivered to site by Sathyaraj ] | Sathyaraj
Sri krishna Sweets Factory | to complete generation meter installation | Manivel | Closed | 2026-05-16 05:30 | [ 29/11/2025 - NFR received ] / [ 10/12/2025 - MRT Discrepancy Letter & Estimate fees for Meter received ] / [ 16/12/2025 - Estimate Fees Paid ] / [ 4th May - Meter & Ct coils are submitted with MRT to calibrate ] / [ 14th May - Meter & Ct Coils are collected form MRT after calibrated ] / 16th May - Generation meter and CT coils are fixed at site as well as wiring done | Manivel
Sri krishna Sweets Factory | to complete the CEIG Process | Manivel | Closed | 2026-05-12 05:30 | [ 1/12/2025 - Waiting for CEIG drawing from Client ] / [ 3/12/2025 - reminder sent, waiting for docs ] / [24/01/2026 - Drawing sent to CEIG office from Essar to get drawing approvals ] / [ 11/02/2026 - drawing Approvals received from Essar ] / [ 17/03/2026 - CEIG Inspection done at site by Essar Control System ] / [ 24/04/2026 - RR Sent to Essar from client , RR itself submit this with CEIG office ] / 11th May 2026 - CEIG Safety received | Manivel
Shoba Silks Pvt Ltd | to complete NFR & Net Meter Process | Manivel | Closed | 2026-05-08 05:30 | [ 27/11/2025- Asked them to share a required docs ] / [ 13/01/2026 - Docs received from them ] / [ 16/02/2026 - CEIG Quote Sent to Vivek by Manivel ] / [ 10/04/2026 - NFR Received ] , [ 22/04/2026 - Quote received for Generation Meter and CT Coil ] / [ 27/04/2026 - Order Placed for CT Coils and Generation Meter ] / [ 29/04/2026 - CT Coils Received from Kalaivani ] / [ 06/05/2026 - Ct coli & generation meters are dispatched to green filed to complete internal wiring ] / [ 07/05/2026 - LTCT Generation meter received from green field ] / | Manivel
Lancor Bagya | to get design confirmation | Manivel | Closed | 2026-01-14 05:30 | [ 12/01/2026 - Drawing request mail sent by Manivel ] / [ 13/01/2026 - Layout Sent to them via mail, Waiting for confirmation ] / [ 14/01/2026 - Got Design Confirmation ] | Manivel
Lancor Ananda | to get design confirmation | Manivel | Closed | 2025-12-09 05:30 | [ 4/12/2025 - Asked CADD file of terrace area to make design by Manivel ] / [ 05/12/2025 - Site Visit done by Manivel and discussed the final location and asked revised design ] / [ 09/12/2025 - Revised design sent and got the confirmation for the same ] | Manivel
Mr Sri Kumar | to send the revised design and get the confirmation for the same | Manivel | Closed | 2026-05-14 05:30 | 3rd Dec 2025 - Design sent to Prem for Confirmation / 14th May 2026 - Prem Asked to start the work at site | Manivel
Mr.Kasinathan | Complete the electrical work | Manikandan | Closed | 2025-12-10 05:30 | [ 03/12/2025 - Electrical Materials delivered & Completed ACDB, DCDB, Earth Pit work ] / [ 04/12/2025 - Inverter installation & termination done by Mohan & Manikandan ] / [ 05/12/2025 - Dc wiring work completed by Manikandan & Mohan ] / [ 06/12/2025 - LA wiring work Completed ] / [ 10/12/2025 - Colum box removal and plastering work has been completed by Sathyaraj team 2 Labour ] | Manikandan
Mr.Rajan Babu | to done system commissioning | Manikandan | Closed | 2025-11-22 05:30 | System commissioned on 22nd Nov 2025 | Manikandan
RWD Grand Corridor | to complete the CEIG Process | Manivel | Closed | 2026-01-06 05:30 | [ 28/11/2025 - Registration process done by Vendor ] / [ 1/12/2025 - Followed them ] / [ 4/12/2025 - Followed them ] / [ 05/12/2025 -Inspection done at site by Suresh ] / [ 06/01/2026 - CEIG Certificate received ] | Manivel
RWD Grand Corridor | to install the net meter at site | Ramachandran | Closed | 2026-01-19 05:30 | [ 20/01/2025 - Net Meter installed by Ramachandran / 21/01/2025 - System commisioned by Mr Anbarasan ] | Anbarasan
Jains Advaya | Yet to Start - to start the electrical work at site | Manivel | Open | 2025-12-08 05:30 | [ 4/12/2025 - Discussed with Vinod for budget ] / Finalize the Vendor for I&C
Mr.Arunkumar | to done system commissioning | Anbarasan | Closed | 2025-11-27 05:30 | [ arunkumar01agu@gmail.com , Solar@123 ] - Deye - Solarman Smart - | Anbarasan
Mr Subramanian | to get design approval | Anbarasan | Closed | 2025-12-15 05:30 | [ 15/12/2025 - Site Visit done by Anbarasan & Mr Lourduraj & got the design confirmation ] | Anbarasan
Ramaniyam Sankaram | Project details | Manivel | Closed | 2025-12-01 05:30 | [ https://maps.app.goo.gl/KSbu8mu2NFHFtXj79 ] / Mr Vijayan / 9841569153 / 4.4 KWp / On grid / Low Raise / RA Puram | Manivel
Ramaniyam Nivasam | Project details | Manivel | Closed | 2025-12-01 05:30 | [ https://maps.app.goo.gl/D7fHrTrrxA6sbast7 ] / Mr Sakkanaguru / 9952919566 / Velachery / 4.4 KWp / On grid / Low Raise | Manivel
Sri Ganapathy Ashram, Phase II | Wi Fi configuration | Suresh | Closed | 2025-08-18 05:30 | ushasankaran1961@gmail.com, Solar123# , | Suresh
Navins Sankalpa | to be done final system commissioning | Manivel | Closed | 2026-04-18 05:30 | 18th April 2026 - Final terminations and system commissioning has been done by Anbarasan & Manikandan, Now the system is working | Manikandan & Anbarasan
Mr Jeyakumar | Project details | Manivel | Closed | 2025-12-04 05:30 | Me Jeyakumar / 8754571288 / On grid / Elevated / DCR / Premier / 600 Wp / 8 Nos / 5 KW / Deye / 3Phase / LA / Civil / Madampakkam [ https://maps.app.goo.gl/uTQwC1FJobcDhdHi8 ] | Manivel
Mr.Anilkumar Mehta - Office | Project details | Manivel | Closed | 2025-11-25 05:30 | 10.4 KWp [ 8.2 KWp DC / 6 KW AC , 2.3 KWp DC / 3.3 kW AC ] , On grid / Non DCR / Elevated / Coimbatore / Civil | Manivel
Lancor Ananda | Project details | Manivel | Closed | 2025-12-01 05:30 | 5 KWp / On grid / Non DCR / Low raise / Mr Jagadeesh / 8940416109 [ https://maps.app.goo.gl/bs2ffbHNUKV5SaTQ8 ] | Manivel
Newry Adora | Project details | Manivel | Closed | 2025-12-01 05:30 | 20 KWp / On grid / Non DCR / Low Raise / Civil Work / Mr Deenadhayalan / 9176227864 / Avadi [ https://maps.app.goo.gl/b21hZvRbNZRrJyid8 ] / 600 Wp - 33 Nos / 20 KW - Deye Inverter | Manivel
Shiroi Energy | Login credential for sungrow inverter | Manivel | Closed | 2025-12-01 05:30 | [manivel@shiroienergy.com,shiro@2025 ]
Shiroi Energy | Login credential for Growatt | Manivel | Closed | 2025-12-01 05:30 | [ EEVUWE001,Solar123 ]
Mr.Anilkumar Mehta - Office | to start & Complete the installation | Anbarasan | Closed | 2025-12-05 05:30 | [ 29/11/2025 - Structure work started for existing sys ] / [ 1/12/2025 - Structure work completed for the exist sys ] / [ 2/12/2025 - Existing sys re wiring & installation completed ] / [ 3/12/2025 - Structure work Started for the new sys & Completed the wiring work for the new sys for both ] / [ 04/12/2025 - Structure & Panel work Completed & Ladder Work in Progress ] / [ 05/12/2025 - Inverter Installation & System work completed , trail run has been done by Anbarasan ] | Anbarasan
SPDPL Padmalaiya | to complete the net meter work | Ramchandran | Closed | 2026-02-04 05:30 | 4th Feb 2026 - Net Meter installed at site by Ramachandran | Ramachandran
Geeyam Suryakantham | to get design confirmation | Manivel | Closed | 2025-12-05 05:30 | [ 27/11/2025 - Earth Pit installation done by Sathyaraj ] / [ 05/12/2025 - Design sent to them for confirmation & Got confirmation ] | Manivel
Geeyam Suryakantham | Project details | Manivel | Closed | 2025-12-04 05:30 | 3.3 KWp / On Grid / Non DCR / 550 Wp - 6 Nos / Renew / Low raise / Raja Annamalai Puram - [ 4/12/2025 - they called and asked to start the installation ] / [ https://share.google/0mUOrRixIg9f6iIDY ] | Manivel
Mr Elumalai | Project details | Mr Manivel | Closed | 2025-03-19 | [ 3.3 KWp / Low raise / DCR / 540 Wp Solex /DCR Panels / 6 Nos / Deye / 3 KW /Single Phase inverter / elumalai_md@yahoo.co.in , Solar123 / pampal / 9940669817 / Elumalai ] | Manivel
Mr Palanivelan | Project details | Mr Manivel | Closed | 2025-03-24 | [ 535Wp / Renew / 6 Nos /DCR / - Deye / 5 KW / three Phase - ppalanivelan@yahoo.co.in, Solar123 ] - [ Kodamapkkam / 9445353666 / Palanivelan ] | Manivel
Geeyam Skandha | Project details | Manivel | Closed | 2025-10-02 05:30 | [ Mr janardhan / 9042989783 / 4.4 KWp , 550Wp/Solex/Bifacial/Non dcr/8Nos/GI Low raise ] | Manivel
Mr Felix Johnson | Project details | Suresh | Closed | 2025-03-20 | 7.5 KWp DC , 5 & 3 KW AC , Elevated , NDCR , Madampakkam | Suresh
Ramaniyam Saranagati / 3.3 KWp | Project details | manivel | Closed |  | [ Mr Palanivelan / 8610648821 , 3.3 KWp , GI Low raise ,Ashok Nagar ] | Manivel
Mr Anandan | Project details | Manivel | Closed |  | [ Anandan/9940687643 / Nolambur / Goldi / 545Wp / DCR /7 NosSungrow/SG4.ORS/12392100283 ] | Manivel
Mr Devadoss / 7 KWp | Project details | Manivel | Closed |  | [ Mr Devadoss / 9444024204 / 6KWp On Grid + 1KWp Off Grid / Pallikkaranai / https://maps.app.goo.gl/mGD7fstp1cdvpkr76 ] | Manivel
Mr Prabakaran | Project details | Manivel | Closed |  | [ Mr Parabakaran / 97899 37512 / Abiramapuram / 550Wp / Adani / DCR / 6Nos / Deye / 3KW / Single Phase / GI Elevated ] | Manivel
Green Crest | Project details | Manivel | Closed | 2025-08-07 05:30 | [ Mr raja / 8754497409 / 9.7 KWp / Low raise / NDCR/ Renew 540Wp / 18 Nos /Growatt inverter / Thirumangalam ] - 9840850345 thirumurugan | Manivel
Shoba Silks Pvt Ltd | Project details | Manivel | Closed | 2025-08-08 05:30 | [ Mr Yuvaraj / 9566133366 / 100 KWp / GI Sheet / Metal Sheet / Vikram / Non dcr / Deye -80 KWp / karapakkam / CEIG - customer scope / TNEB - shiroi Scope / Sprinkler required ] | Manivel
Mr Siva Elango | Project details | Manivel | Closed | 2025-08-08 | [ Mr Siva / 9840082998 / 5 kWp / On Grid / Elevated / DCR / Adani / Deye / Civil - Customer Scope / LA - Not required / TNEB - Customer scope / Virumgampakkam ] | Manivel
Mr Shanmugam | Project details | Manivel | Closed | 2025-08-07 | [ Mr Shanmugam / 9884466793 / 5.5 kWp / NDCR / Panasonic or Renew / 550 Wp / 10 Nos / On grid / Low Raise / LA - Not reuired / Net Meter - shiroi Scope / Civil Work - Client Scope / 4/54 , kaveri Rangan Nagar , Saligramam] | Manivel
Mr Arjun Prasath | Project details | Manivel | Closed | 2025-09-10 | [ 9543886574 / Vijaykumar / NDCR / Waaree / 690 Wp / Low raise & Elevated / LA & civil - Shiroi Scope / Mylapore] | Manivel
CM Construction | Project details | Manivel | Closed | 2024-08-24 | 3.3 KWp / On Grid / Elevated / Non DCR / Waaree / 540Wp - 6 Nos / Havells - 4 KW/ Single Phase / Nerkundram | Manivel
SPDPL Luz Avenue | Project details | Manivel | Closed | 2024-08-31 05:30 | [ 8 KWp / Non DCR / Elevated / On Grid Systems / Luze Avenue / 8 KW inverter Three Phase ] | Manivel
SPDPL Padmalaiya | Project details | Manivel | Closed | 2025-10-10 | [ 4.4 KWp / Non DCR / Elevated / On grid systems / Alwarpet / 4 KW Inverter Single Phase ] | Manivel
Newry Adora | complete the str & panel installation | Sathyaraj | Closed | 2025-12-08 05:30 | [ 06/12/2025 - 33 No Solar Panels & structure Materials shifted to terrace by Sathyaraj team ] / [ 09/12/2025 to 12/12/2025 - Str & panel installation completed by Suresh & sathyaraj team ] | Sathyaraj & Suresh
Geeyam Skandha | to complete the net meter work | Ramachandran | Closed | 2025-12-05 05:30 | [ 04/12/2025 - Net meter installed at Site by Ramachandran ] / [ 05/12/2025 - Sys Commissioning has been completed by Suresh] / the system is working within the operating Limits | Suresh
Geeyam Skandha | to start & Complete the installation | Anbarasan | Closed | 2025-11-05 05:30 | [ 05/11/2025 - Inverter Delivered to site & completed the final termination by Suresh & Anbarasan ] | Anbarasan
Kalakchetra | to complete the net meter work | Ramachandran | Open | 2025-12-08 05:30 | [ 04/12/2025 - Waiting for Normal Meter connection , Spoken on 04/12/2025 by Manivel ]
Sri krishna Sweets | to complete the net meter work & CEIG Process | Ramachandran | Open | 2026-04-25 05:30 | [ 04/12/2025 - Spoken with Muthu Raman for Load increase & name Change by Manivel ] / [ 27/04/2026 - Covering letter, Drawings & form A1 shared with client to get signature by Manivel ] / [ 02/05/2026 - Spoke with Muthu Raman, he got signed copy today. yet to submit this with ESSAR by EOD ] /
Sri krishna Sweets | to start & Complete the installation | Anbarasan | Closed | 2025-11-28 05:30 | [ 24/11/2025 - Started the installation work at site by Contractor Rajesh & Completed on 28/11/2025 ] | Anbarasan
Mr Jeyakumar | to get design confirmation | Manivel | Closed | 2025-12-11 05:30 | [ 05/12/2025 - Panel Enquired with Solstrom and share the quote with Vinod by Manivel ] / [ 11/12/2025 - Panel delivered to site from Solstrom by Manikandan & Mohan & Fabricator site visit also completed by Lourduraj & Final design sent to customer ] | Manikandan & Mohan
Mr.Anilkumar Mehta - Office | to complete the net meter work | Ramachandran | Closed | 2026-02-04 05:30 | [ 13/01/2026 - Net Meter installed for 8 KWp Soar system and system commissioning has been completed by Anbarasan ] / [ 03/02/2026 - Net Meter installed at site ] / [ 04/02/2026 - Final system commissioning and demo completed by Anbarasan ] | Anbarasan
Mr.Kasinathan | to complete the net meter work | Ramachandran | Closed | 2025-12-08 05:30 | [ 09/12/2025 - Net Meter installed at SIte By Ramachandran ] / [ 10/12/2025 - Final System Commissioning has been done by Manikandan , the system is working within the operating Limits ] | Ramachandran
Mr.Kasinathan | Project details | Manikandan | Closed | 2025-11-26 05:30 | [ 4.4 KWp , 2.2 KWp - DCR & 2.2 KWp - NDCR ] / On Grid / Elevated / [ https://maps.app.goo.gl/s9Ur9XCcL1XBAxAD9 ] - Palavanthangal / 9994453354 | Manikandan
Rakshas Enterprises | to start & Complete the installation | Anbarasan | Closed | 2025-12-08 05:30 | [ 06/12/2025 - Electrical work completed for the AC Side & Structure work initiated ] / [ 07/12/2025 - Structure work 50% Completed ] / [ 08/12/2025 - Structure Work and Panel installation, Civil Work Completed ] | Anbarasan
Rakshas Enterprises | Project details | Anbarasan | Closed | 2025-12-01 05:30 | [ 9.8 KWp DC / 8 KW AC - 580 Wp / Adani / 17 Nos / 8 KW / On Grid Inverter / Sun grow ] - Hopes [ Mr Saravanan / 9942245201 ] | Anbarasan
Mr Srinivasan Adyar | Project details | Manivel | Closed | 2025-12-10 05:30 | [ 6 KWp DC , 6 KW AC - Hybrid Systems , Elevated / NDCR , Adani / 600 Wp - 10 Nos, Deye 6 KW Hybrid three phase , 2 Nos 48 Ah Battery , LA, Civil ] | Manivel
Mr Srinivasan Adyar | Contact details | Premkumar | Closed | 2025-12-10 05:30 | [ Srinivasan / 9810289083 , Karpagam garden, Adyar ] / [ https://maps.app.goo.gl/n6qnXbVmQ8PaPChc6 ] | Premkumar
Mr Saravanan 4 Bricks | Project details | Premkumar | Closed | 2025-12-10 05:30 | [ 3.3 KWp DC, 3 kW AC, NDCR , Vikram 550 Wp - 6 Nos , On grid , Elevated , Civil & LA - client Scope ] | Premkumar
Mr Saravanan 4 Bricks | Contact details | Premkumar | Closed | 2025-12-10 05:30 | [ Mr Saravanan , 9094039650 , RBI Colony , Adyar https://maps.app.goo.gl/sCGX89L6A19YhVRz8 ] | Premkumar
Lancor Ananda | to deliver the str & panels to site | Manivel | Closed | 2025-12-13 05:30 | [ 10/12/2025 - Structure order Placed with green field , And Confirmed panel make with vinod , renew 550 Wp , 9 Nos ] - [ 13/12/2025 -Str & panels delivered to site by Mohan ] | Mohan
Mr Raja grn gopal street | to complete the str & Panel installation | Manivel | Closed | 2026-02-11 05:30 | [ 12/11/2025 - 15/11/2025 - Structure Work Completed at site by Lourduraj ] - [ 10/12/2025 -Spoke with them by Manivel ] / [ 07/02/2026 - Panels delivered to site and shifted to terrace by Sathyaraj & two labours ] / [ 10/02/2026 & 11/02/2026 - Panels installation and paint work completed by Lourduraj ] | Manivel
Mr Raja grn gopal street | Project details | Manivel | Closed | 2025-11-11 05:30 | [ 9.9 KWp - 2.2*3 Nos, 3.3 *1 Nos ] , DCR - Adani / 550 Wp / 18 Nos ] / Elevated | Manivel
Mr Raja grn gopal street | Contact details | Manivel | Closed | 2025-11-11 05:30 | [ Mr Raja / 9444376987 , Site Engineer - 9940011125 ] /[ https://maps.app.goo.gl/1QzkmcdZrKpceiV5A] / West Mambalam | Manivel
Ramaniyam Sankaram | complete the str & Panel installation | Mohan | Closed | 2025-12-09 05:30 | Structure & panels shifted to terrace and completed the installation for the same at site Suresh & Mohan, Manikandan with two labours for shifting | Mohan
Ramaniyam Nivasam | to complete the str & panel installation | Suresh & Mohan | Closed | 2025-12-10 05:30 | [ 10/12/2025 - Str & Panel installation work completed by Suresh & Mohan, with 2 Labour used for shifting ] | Suresh & Mohan
Mr Sridhar Rajan | Project details | Manivel | Closed | 2025-09-10 05:30 | [ 6 KWp DC, 6 KW AC, On Grid Elevated , DCR ] / [ Site Engineer ,Tamil / 9094743332 , [ https://maps.app.goo.gl/1vtzAPjp4LrizHJt9 ] / Madipakkam [ Mr Sridhar rajan 7358667157 ] | Manivel
Mr Sridhar Rajan | to complete the str work | Paulpandi | Closed | 2025-09-24 05:30 | [ 24/09/2025 - Structure & Panel installation completed by Lourduraj , Earth pit & conduit laying work completed up to floor level by Paulpandi ] | Paulpandi
Newry Astor | to complete the sys commissioning | Suresh | Closed | 2025-12-11 05:30 | [ 10/11/2025 - Net meter installaed at site by Ramachandran ] / [11/12/2025 - System commissioning has been done by Suresh ] | Suresh
Mr Jeyakumar | to complete the str & Panel installation | Manikandan | Closed | 2025-12-17 05:30 | [ 16/12/2025 - Structure Post errection completed by Lourduraj ] / [ 17/12/2025 - Str & Panel installation completed by Lourduraj] | Mohan
Geeyam Suryakantham | to deliver the str & panels to site | Manivel | Closed | 2025-12-13 05:30 | [ 11/12/2025 - str order placed with green field, panel order placed with southern power , 550Wp*6 Nos,NDCR ] / [ 13/12/2025 -Str & panels delivered to site by Mohan ] | Mohan
Mr Sridhar Rajan | to complete the electrical work | Manivel | Closed | 2025-12-31 05:30 | [ 11/12/2025 - 8 KW inverter received at office by Manivel from inspire energy ] / [ 31/12/2025 - Inverter installed at site and system commissioning has been completed ] | Manikandan & Anbarasan
Mr Nitin | Project details | Manivel | Closed | 2025-12-12 05:30 | [ https://maps.app.goo.gl/6HZvxyzsiBHQnDXcA ] / [ 6 KWp / 6 KW AC / Adani / DCR / 620Wp*10 Nos ] / [ +91 98401 86664 / Purushottam ] / LA & Civil - Shiroi / On grid / Elevated | Manivel
DRA Optima | to complete the - installation | Manikandan | Closed | 2025-12-12 | [ 12/12/2025 - Adhisive apply & Panel relocation , earth chmaber work has been completed by Manikandan & Sriram contractor ] | Manikandan
DRA Optima | to complete the system commissioning | Manivel | Closed | 2026-01-08 05:30 | [ 08/01/2026 - Net Meter installed at site by Client Side ] / [ 08/01/2026 - Final System commissioning has been done and inverter is working normal ] | Manikandan & Mohan
DRA Urbania | to complete the system commissioning | Manivel | Closed | 2026-01-08 05:30 | [ 08/01/2026 - Net Meter installed at site by client Scope ] / [ 08/01/2026 - System commissioning has been done by Manikandan ] | Manikandan
DRA Skylanties | to complete the earth cable conduit work | Sathyaraj | Closed | 2026-02-20 05:30 | [ 29/01/2026 - Coduits ar laid to provision for earth cable by sathyaraj ] / [ 19/02/2026 - Chmaber Fixing work and conduit laying work done by Sathyaraj with one labour ] | Sathyarj
DRA Skylanties | to complete the str work | Mohan | Closed | 2025-09-09 05:30 | Str installation & Pedestal work for the post completed for the 14 KWp system | Mohan
DRA Skylanties | Project details | Manivel | Closed | 2025-09-01 | [ 19 KWp - 14 & 5 kWp ] / [ Mr Saravanan / 9566292572 ] / [ On grid / Low Raise ] / [ Navalur ] | Manivel
Luxebuilt Homes Pvt ltd | to complete the system commissioning | Anbarasan & Manikandan | Closed | 2025-12-13 05:30 | [ 11/12/2025 - Net Meter installed at site by Ramachandran ] / [ 13/12/2025 - System commissioning done by Manikandan & Anbarasan , the system is working ] | Manikandan & Anbarasan
Mr Nitin | to delivery the Panels & str to site | Suresh | Closed | 2025-12-16 05:30 | [ 13/12/2025 - str materials delivered to site by Rajesh welder ] / [ 15/12/2025 - Structure post errection work completed ] / [ 16/12/2025 - Str & Panel work completed ] | Suresh
Ramaniyam Nivasam | to complete the electrical work | Manikandan | Closed | 2025-12-23 05:30 | 22nd Dec 2025 - Electrical Materials delivered to site and started installation / 23rd Dec 2025 - Except Inverter, All wiring work has been done | Manikandan & Anbarasan
Ramaniyam Sankaram | to prepare bill of items & deliver the same to site | Manivel | Open | 2025-12-15 05:30
SPDPL Padmalaiya | to re route the dc wiring | Suresh | Closed | 2025-11-27 05:30 | 27th Nov 2025 - DC cable re route wiring work done by Suresh | Suresh
Newry Adora | to get site clearance | Manivel | Closed | 2026-05-31 05:30 | got site clearance | Premkumar
Lancor Ananda | to install the str & Panels | Manikandan & Anbrasan | Closed | 2025-12-15 05:30 | [ 15/12/2025 - Str & panels shifted to terrace by Sathyaraj team 2 labours and installed the same at site by Manikandan & Anbarasan ] | Manikandan & Anbarasan
Mr Srinivasan Adyar | to get design confirmation & site visit for bill of items | Manivel | Closed | 2026-01-13 05:30 | [ 16/12/2025 - Went site visit to check the design, there is required to modify the designs by Manivel ] / [ 13/01/2026 - Final Site meeting done along with fabricator & architect , client , the system design approved ] | Manivel
Mr Subramanian | Project details | Manivel | Closed | 2025-12-15 05:30 | [ 2* 3 KWp DC / 2*3 KW AC / On Grid / Elevated / DCR / Premier / 600 Wp * 10 Nos / Growatt / 3 KW* 2 Nos / Koturpuram / LA / Civil / https://maps.app.goo.gl/RyxzrZvwTsyinVsY9 / 9841023587 ] ] | Manivel
Mr Subramanian | to deliver the str & panels to site | Manivel | Open | 2025-12-18 05:30
Mr Nitin | to complete the civil work at site | Sathyaraj | Closed | 2026-01-05 05:30 | [ 17/12/2025 - Civil work completed by Sathyaraj & 2 Labours ] | Sathyaraj
Mr Nitin | to complete the electrical work | Suresh & Mohan | Closed | 2025-12-20 05:30 | [ 20/12/2025 - Electrical work completed , Waiting for Net Meter ] | Suresh & Mohan
VM Builder | Project details | Manivel | Closed | 2025-12-26 05:30 | [ 5 KWp / Adani / 620 Wp / DCR / On Grid / Elevated / LA / Civil / 7358195224 / Mahendran / https://maps.app.goo.gl/Vt5Yji77D3ESPH7YA ] | Manivel
Shankaran - Shree Viruksha | Project details | Manivel | Closed | 2025-12-26 05:30 | [ 2 KWp * 4 Nos / DCR / Adani / 550 Wp / Sathik / 7845578355 / Besant Nagar, LA & Civil - Customer Scope / https://maps.app.goo.gl/h3ZCZ8wLKdzwQWQC9 ] | Manivel
Swarnalatha | Project details | Manivel | Closed | 2026-01-03 | [ DCR / 4.3 KWp / Elevated / Adani / 620 Wp / 7 Nos / LA & Civil - Shiroi / 8754496322 / https://maps.app.goo.gl/yMFTsL4UtkzTTwbq5 ] | Manivel
Ramaniyam Manasa | Project details | Manivel | Closed | 2026-01-03 | [ 8.8 KWp / NON DCR / Low Raise / On grid / Anna Nagar / Site Eng Mr Ganesh / 7299111125 / 8 KW Inverter / Deye / https://maps.app.goo.gl/dxbcs8gStuondizb6] | Manivel
Khurinji's Orchid | Project details | Manivel | Closed | 2026-01-03 | [ 5 KWp / NDCR / On Grid / Elevated / Mr Pruthiviraj / 9840868033 / https://maps.app.goo.gl/JtX49QihjMFe81No8 ] | Manivel
Ramaniyam Gayathri | Project details | Manivel | Closed | 2026-01-02 05:30 | [ 4.4 KWp / NDCR / On Grid / LOw Raise / Mr Prabhu / 9841269052 / Thiruvanmiyur / https://maps.app.goo.gl/yhEHYkSH9kA2Rvbm7] | Manivel
Mr Nitin | to install net meter | Ramachandran | Closed | 2025-12-26 05:30 | [ 26/12/2025 - Net Meter installed at site & commissioning done ] | Ramachandran
VM Builder | to complete str Work | Manikandan | Closed | 2026-01-03 05:30 | [ 31/12/2025 to 03/1/2026 - Structure Materials delivered to site & Completed by Lourduraj with One full Coat Painting ] | Manikandan
VM Builder | to complete the electrical work | Manikandan | Closed | 2026-01-03 05:30 | [ 02/01/2026 to 03/01/2026 - Electrical materials delivered to site and completed all work by Manikandan & Mohan ] | Manikandan & Mohan
VM Builder | to complete the civil Work | Sathyaraj | Closed | 2026-01-13 05:30 | Civil Work completed | Sathyaraj
Lancor Lumina ABC | Project details | Manivel | Closed | 2026-01-06 05:30 | [ 20 KWp / Low Raise , On Grid , Guduvanchery / https://maps.app.goo.gl/pfiz8y8fy8GbdCe26 / 99942 98783 / Ramanathan ] | Manivel
Lancor Lumina ABC | to delivery the Panels & str to site | Manivel | Closed | 2026-01-07 05:30 | [ Str & Panels delivered to site - un loaded by labours ] | Manivel
Lancor Lumina ABC | to complete the str & panel installation | Manivel | Closed | 2026-01-09 05:30 | [ 07/01/2026 - Structure Materials shifted to terrace & completed installation by Sriram labours / 4+4 Nos ] / [ 08/01/2026 - 34 Nos Panels shifted to terrace - 4 Labours ] / [ 09/01/2026 - Panel installation completed by Sriram labour 4 Nos ] | Manivel
S&P Courtyard | to complete electrical work - all three towers | Manivel | Open | 2026-02-25 05:30 | [ 24/02/2026 - All electrical materials are ready at Shiroi Office , yet to dispatch to site ] /
Geeyam Suryakantham | Complete the electrical work | Manikandan & Mohan | Closed | 2026-01-14 05:30 | [ 12/01/2026 - Electrical Materials delivered to site and completed DC wiring & inverter installation by Manikandan & Mohan] / [ 13/01/2026 - AC Wiring & Earth wiring Com Mohan ] | Manikandan & Mohan
Geeyam Suryakantham | to complete the net meter work | Ramachandran | Closed | 2026-02-04 05:30 | [ 03/02/2026 - Net Meter installed by Ramachandran ] / [ 04/02/2026 - System commissioning done by Manikandan ] | Manikandan
Geeyam Prasang | to deliver the str & panels to site , Installation | Manikandan & Mohan | Closed | 2026-01-13 05:30 | [ 12/01/2026 - Panels delivered to site by Sathyaraj ] / [ 13/01/2026 - Structure delivered to site by Manikandan & installed structure , Panels at site with help of two labours ] | Manikandan & Mohan
Geeyam Prasang | to complete the electrical work | Manikandan | Closed | 2026-01-21 05:30 | [ 20/01/2026 - 21/01/2026 - Electrical materials delivered to site and completed the same at site by Manikandan & Mohan] | Manikandan & Mohan
Jains Aadheeswar | to complete the final termination & install the generation meter | Manivel | Open | 2026-01-19 05:30 | Waiting for Net Meter & CEIG - Client Scope
Khurinji's the Orchid | to delivery the Panels & str to site | Manivel | Closed | 2026-01-07 05:30 | [ 03/01/2026 - Panels delivered to site by Manivel & Keshav ] / [ 07/01/2026 - Panels Shifted to terrace and fixed as temporary arrangements to get a CC, Supplied triangle structure to site by Sathyaraj & 3 Labours ] | Sathyaraj
Khurinji's the Orchid | to get site clearance | Manivel | Closed | 2026-03-11 05:30 | [ 09/03/2026 - Site Clearance got and deisgn confirmation got on 11/03/2026 by Manivel ] | Manivel
Lancor Bagya | to deliver the str & panels to site | Manivel | Closed | 2026-01-28 05:30 | [ 23/01/2025 - Panels received at Shiroi office ] / [ 24/01/2026 - Structure order placed with green field ] / [ 29/01/2026 - Structure and panels delivered to site by Anbarasan & Manikandan ] | Manikandan & Anbarasan
Ramaniyam Anugraha | to done system commissioning | Manikandan & Mohan | Closed | 2026-01-14 05:30 | [ 13/01/2026- Net Meter installed at site ] / [ 14/01/2026 - System Commissioning done and system is working normal ] | Manikandan & Mohan
Zeneto infra | Project details | Manivel | Closed | 2025-11-01 05:30 | [ 3.3 KWp / Low Raise / On Grid / Non DCR / Velachery / https://maps.app.goo.gl/AsjP3UeYq8yGMzjR8 / 82205 42028 - Site Eng ] | Manivel
Felix Johnson | to change meter connection | Manikandan | Closed | 2026-01-22 05:30 | Meter connection inter changed | Manikandan
Adroit Prosper D Block | Project details | Manivel | Closed | 2026-01-25 05:30 | [ 10 KWp / 10 KW AC , On Grid , GI Low Rise , Growatt Inverter, Vikram Panel , Thalambur ] | Manivel
Adroit Prosper D Block | site visit | Manivel | Closed | 2026-01-24 05:30 | Went site and discussed the panel location and table arrangements to construct the pedestal work , Civil Work client scope | Manivel
DRA Urbania | to complete demo & get signature in the commissioning report | Manikandan | Closed | 2026-01-27 05:30 | Demo for MEP Manager Selvam , completed for bith tower urbania & optima | Manikandan
Mr Sundar | Project details | Manivel | Closed | 2026-01-20 05:30 | [ 5.5 KWp / 5 KW AC, On Grid / Elevated / DCR / https://maps.app.goo.gl/d9gtAhirro9ZzX8m9 / Mr Sundar / 98410 87323 / LA & Civil - Shiroi ] | Manivel
Mr Sundar | to complete the str & panel installation | Manikandan | Closed | 2026-01-22 05:30 | [ 20/01/2026 - 22/01/2026 - Structure & Panel installation work completed by Mr Lourduraj ] | Manikandan
Mr Sundar | to complete the electrical work | Manikandan | Closed | 2026-01-23 05:30 | [ 22/01/2026 - Electrical Materials delivered to site and started work by Contractor Sriram] / [ 23/01/2026 - Electrical work and earth pit installation work completed by contractor Sriram ] | Manikandan & Manivel
Mr Sundar | to complete civil work & floor painting | Sathyaraj | Closed | 2026-01-29 05:30 | [ 27/01/2026 - Civil materials delivered to site and completed the 6 Nos pedestal work by Sathyaraj & 3 Labours ] / [ 28/01/2025 - Plastering work and earth pit chamber work completed by Sathyaraj & 3 Labours ] | Sathyaraj
Mr Sundar | to complete net meter installation | Ramachandran | Closed | 2026-02-04 05:30 | [ 03/02/2026 - Meter installed at site ] / [ 04/02/2026 - System commissioning and demo done by Manivel ] | Manivel
Adroit Prosper D Block | to deliver the str & complete the installation | Anbarasan | Closed | 2026-03-17 05:30 | 16th March - Structure delivered to site / 17th March - structure installation done by Anbarasan | Anbarasan & Mohan
Mr Srinivasan Adyar | to complete the str & panel installation | Manivel | Closed | 2026-01-15 05:30 | [ 14/01/2026 - Structure Materials & panels delivered to site and work initiated by Lourduraj ] / [ 15/01/2026 - Structure & Panel Work completed by Lourduraj ] | Manivel
Mr Srinivasan Adyar | to check load details for back up lines | Manivel | Closed | 2026-01-28 05:30 | [ 13/01/2026 - Discussed with Architect and customer about the backup load details ] / [ 24/01/2026 - They have shared the no of load for back up calculations ] / [ 27/01/2026 - Have shared the load details with Prem and architect to confirm the loads ] / [ 09/02/2026 - Manikandan & electrician discussed about load details with Client ] / | Manivel
Mr Sridhar Rajan | to complete structure re painting work | Manikandan | Closed | 2026-01-27 05:30 | [ 23/01/2026 - Structure base painting work completed by Lourduraj ] / [ 27/01/2026 - Structure Painting work completed and system re commissioning has been done by Lourduraj & Manikandan ] | Manikandan
Abirami Eng Cons & Co | to complete the final terminations & sys commissioning | Manivel | Closed | 2026-05-08 05:30 | [ 07/04/2025 - Final termination & system commissioning done by Manikandan & Mohan ] / [ 08/06/2026 - Commissioning report & handover report sent to them via mail by Manivel ] | Manikandan & Mohan
Mr Saravanan 4 Bricks | to complete the electrical work | Anbarasan | Open | 2026-01-29 05:30 | [ 27/01/2026 - Electrical Materials & Panels delivered to site , completed DC wiring work by Anbarasan & Mohan ] / [ 28/01/2026 - Mini Rails delivered to site and completed panel installation by Anbarasan & Manikandan ] / to complete wiring | Anbarasan
Lancor Bagya | to complete the str & panel installation | Sathyaraj | Closed | 2026-01-30 05:30 | [ 30/01/2026 - Structure & Panels shifted to terrace and completed the installation for the same - with 3 Labours] | Sathyaraj
Lancor Bagya | to get site clearance | Manivel | Open | 2026-02-05 05:30 | site clearance for rest of electrical works
Ramaniyam Manasa | to deliver the str & panels to site | Manikandan & Mohan | Closed | 2026-01-28 05:30 | [ 22/01/2026 - Panels delivered to site by Mohan & Anbarasan ] / [ 28/01/2026 - Structure delivered to site and shifted to panels, structure to terrace by Mohan & 3 Labours ] | Mohan
Mr Sankaranarayanan | Project details | Manivel | Closed | 2025-06-16 05:30 | [ Mr Sankaranarayan / 9789948922 / Deye 3 KW / On Grid / Elevated / Madampakkam ] | Manivel
Ramaniyam Manasa | to complete str & panel installation | Manikandan & Mohan | Closed | 2026-01-31 05:30 | [ 30/01/2026 - Str installation completed by Manikandan & Mohan ] / [ 31/01/2026 - Panels installation completed by Manikandan & Mohan ] | Manikandan & Mohan
DRA Skylanties | to deliver the panels to site and complete installation at tower A | Sathyaraj | Closed | 2026-02-02 05:30 | [ 21/01/2026 - 34 Nos / Panels are delivered to site and stored ground floor by sathyaraj along with rental panels 30 Nos ] / [ 24/01/2026 - Rental panels are shifted to terrace by sathyaraj & team 3 Nos ] / [ 29/01/2026 - Rental panels fixed at site and permanent panels are shifted to 13th floor from ground floor by sathyaraj & team 3 Nos ] | Sathyaraj
Zeneto infra | to complete electrical work | Anbarasan & Manikandan | Closed | 2026-02-02 05:30 | [ 02/02/2026 - Electrical Materials delivered to site and completed the same at site , Structure & panel work also done by Mr Rajesh ] | Manikandan, Anbarasan & mohan
Zeneto infra | to complete the final termination and system commissioning | Manivel | Open | 2026-02-10 05:30 | Waiting for Net meter / Meter Shiroi Scope
Ramaniyam Rangavilasam | Project details | Manivel | Closed | 2026-02-03 05:30 | [ https://maps.app.goo.gl/XJHpbu3nLAnMF6jb7 / 4.4 KWp / On Grid Low Rise / Nanganallur / 98842 24570.- Govindaraju ] | Manivel
Ramaniyam Gayathri | to complete the str & panel installation | Sathyaraj | Closed | 2026-02-10 05:30 | [ 03/02/2026 - Structure and panels are shifted to terrace with three labours and structure along with 5 panel installation done ] / [ 10/02/2026 - Panels installed by Manikandan & Mohan ] | Manikandan & Mohan
Ramaniyam Manasa | to complete the electrical work | Manikandan & Mohan | Open | 2026-02-04 05:30
Ramaniyam Rangavilasam | to deliver the str & panels to site | Sathyaraj | Closed | 2026-02-04 05:30 | [ 04/02/2026 - Structure & Panels delivered to site and shifted to terrace , installation also has been done by sathyaraj & 3 labours ] | Sathyaraj
Zirve Project | Project details | Premkumar | Closed | 2026-02-05 05:30 | [ 97871 55908 / Viswanathan / https://maps.app.goo.gl/ehWhHdhUCjVasfoX7 / Saligramam / On grid / Low Rise / Non DCR / 30 KWp / 25 KW AC ] | Premkumar
VM Builder | to complete the net meter work | Ramachandran | Closed | 2026-01-28 05:30 | [ 27/01/2026 - Net Meter installed at site ] / [ 28/01/2026 - System commissioning done by Manikandan ] | Manikandan
RWD Grand Corridor | to give demo to associate people | Manivel | Closed | 2026-02-04 05:30 | [ 04/02/2026 - Demo completed ] | Manivel
Ramaniyam Rangavilasam | to complete the electrical work | Manivel | Closed | 2026-02-11 05:30 | 10th Feb 2026 - Electrical Materials delivered to site by Sathyaraj & 2 labours and completed the AC wiring & inverter installation / 11th Feb 2026 - All electrical work done by Sathyaraj , except final terminations | Sathyaraj
S&P Courtyard | Project details | Manivel | Closed | 2024-12-07 05:30 | [ 10 KWp DC / 8 KW AC - 3 Nos ] / 335 Wp - 60 Nos / Deye 8 KW - 3 Nos / Civil & LA - Client Scope / Senthil Kumar / 9789489407 ] | Manivel
M/s Geetha Kalyan | Project details | Premkumar | Closed | 2026-02-07 05:30 | [ 600 Wp / 3 Nos / 1.8 KWp / 2.2 KW / On grid / Elevated / 9884216729 / Geetha / https://maps.app.goo.gl/9zhkPadVnf2iN4fC7 / RA Puram ] | Manivel
Mr Manickam | Project details | Premkumar | Closed | 2026-02-07 05:30 | [ Mr Manickam / 9629205487 / 1.2 KWp DC / 1.5 KW AC / Adani / 620 Wp / On Grid / Elevated / DCR / Thuraipakkam / https://maps.app.goo.gl/KdY2HAznt3mqz1E77 ] | Manivel
Mr Aditya Baskar | Project details | Premkumar | Closed | 2026-02-07 05:30 | [ 4.2 KWp DC / 4 KW AC / Adani / 600 Wp - 7 Nos / DCR / Elevated / Mr Aditya Baskar - 9790895977 / LA & Civil / https://maps.app.goo.gl/KdY2HAznt3mqz1E77 / Thuraipakkam ] | Manivel
Ekana Cottage | Project details | Manivel | Closed | 2026-02-10 05:30 | [ 8 KWp / 8 KW AC , ON Grid , Non DCR , Mini Rails , Alwarpet , 9361999911 / Satheesh / https://maps.app.goo.gl/eB4U7cpySJwaDSK76 ] | Manivel
Mr.Karthikeyan / CM Constructions | to complete the net meter work | Ramachandran | Closed | 2026-02-08 05:30 | [ 08/02/2026 - Net Meter installed at site ] / [ 10/02/2026 - System commissioning done by Manikandan & Wi Fi configuration also has been done ] | Manikandan
Zirve Project | to get design confirmation & site visit for bill of items | Manivel | Open | 2026-03-24 05:30 | [ 05/02/2026 - Site Visit done and drawing request mail sent , drawing received, asked design with design team ] / [ 12/02/2026 - Received design from team and shared the same with client via mail ] / [ 23/03/2026 - They asked to site visit to explain the module ] /
Ramaniyam Gayathri | to complete the electrical work | Manikandan & Mohan | Closed | 2026-02-10 05:30 | [ 07/02/2026 - Electrical Materials delivered to site and completed the AC , Inverter wiring by Manikandan & Mohan ] / [ 10/02/2026 - DC wiring and termination completed by Manikandan & Mohan ] | Manikandan & Mohan
Ramaniyam Gayathri | to complete the sys commissioning | Manivel | Closed | 2026-05-16 05:30 | 16th May 2026 - System Commissioning done by Anbarasan | Anbarasan
RCC e Constrcution 2 | to complete the LA Installation & termination 🚨 | Manikandan & Mohan | Open | 2026-02-13 05:30 | [ 12/02/2026 - Tower A, LA installation and wiring work done by Manikandan & Mohan ] / [
M/s Geetha Kalyan | to complete the str & panel installation | Mohan | Closed | 2026-02-14 05:30 | [ 14/02/2026 - Str & panel installation completed by rajesh welder ] | Mohan
M/s Geetha Kalyan | to complete the civil work | Sathyaraj | Closed | 2026-02-17 05:30 | [ 17/02/2026 - Civil Work Completed by Sathyaraj ] | Sathyaraj
Mr Aditya Baskar | to complete the str & panel installation | Manikandan | Closed | 2026-02-16 05:30 | [ 13/02/2026 - Str and panels delivered to site and shifted them into terrace by Lourduraj ] / [ 14/02/2026 - Structure Post Erecting completed by Lourduraj ] / [ 16/02/2026 - Panel installation done by Welder ] / [ | Manikandan
Mr Manickam | to complete the str & panel installation | Manikandan | Closed | 2026-02-16 05:30 | [ 13/02/2026 - Structure & panels delivered to site and shifted them into terrace by Lourduraj ] / [ 14/02/2026 - Structure post erecting done by Lourduraj ] / [ 16/02/2026 - Panel installation done by Welder ] | Manikandan
Accord Foundtaions | Project details | Manivel | Closed | 2026-02-14 05:30 | [ 30 KWp DC / 33 KW AC / Solar edge inverter with optimizer / Elevated / On Grid / Non DCR / LA & Civil - Shiroi Scope / https://maps.app.goo.gl/eAZ1Suzw69vPBbFB9 ] | Manivel
Accord Foundtaions | to complete the str & panel installation | Manivel | Open | 2026-03-05 05:30 | [ 23/02/2026 - Got Site Clearance form them to start the str work at site ] / Yet to Start Str
Mr Vasu rao | Project details | Premkumar | Closed | 2026-02-19 05:30 | [ 4.2 KWp / 4 KW AC , On grid / DCR / Elevated / Adani / 600 Wp - 8 Nos , 4 KW inverter , deye , Single phase , LA & Civil - Shiroi Scope / Teynampet / https://maps.app.goo.gl/1eviA6inXGSYEABp6 / 9444079791 ] | Premkumar
Mr Vasu rao | to deliver the str & panels to site | Manivel | Closed | 2026-02-27 05:30 | [ 21/02/2026 - Site Visit along with Welder done by Manivel ] / [ 26/02/2026 - Str & Panels delivered to site and initiated the str work by Rajesh welder ] / [ 27/02/2026 - Str and panel installation completed by Rajesh welder ] | Manikandan Sirkali
M/s Geetha Kalyan | to complete the electrical work | Mohan | Closed | 2026-02-24 05:30 | [ 21/02/2026 - Electrical Materials delivered to site and initiated the work by Mohan & Manikandan ] / [ 23/02/2026 - Except final termination all the work has been completed by Mohan & Manikandan ] / [ 03/03/2026 - Final Termination done by Manikandan & Mohan ] | Mohan & Manikandan
Syed Mubarak | Project details | Manivel | Closed | 2026-02-24 05:30 | [ 6.3 KWp / 6 KW AC / On grid Elevated / Non DCR / https://maps.app.goo.gl/qu2EPEz7LYLWD3cW8 / Manapakkam / Waaree / 700 Wp - 9 Nos / Mr Yuvaraj / 95661 33366 / Civil & LA - Shiroi Scope ] | Manivel
Ekana Cottage | to deliver the str & panels to site | Manivel | Closed | 2026-03-02 05:30 | [ 02/03/2026 - Panels & electrical materials are delivered to site by Manikandan Sirklai & installed the panels & structure work by Contractor Sriram ] | Manikandan Sirkali
Syed Mubarak | to deliver the str & panels to site | Manivel | Closed | 2026-03-06 05:30 | [ 04/03/2026 - Structure & Panels delivered to site by Lourduraj and shifted them to terrace ] / [ 05/03/2026 - Post installation completed ] / [ 06/03/2026 - Panels & structure installation work completed by Lourduraj ] | Manivel
Mr Vasu rao | to complete the electrical work | Manikandan & Mohan | Closed | 2026-03-02 05:30 | [ 28/02/2026 - Electrical materials delivered to site by Manikandan Sirkali & Completed the Inverter, ACDB , DCDB & Ac wiring & Earthing Work ] / [ 02/03/2026 - DC Wiring & LA Work completed , Civil Work also done by Sathyaraj team ] | Manikandan & Mohan & Sathayarj
DRA Trinity | Project details | Premkumar | Closed | 2026-02-28 05:30 | [ 35.2 KWp / 35 KW AC , On Grid / Non DCR / Low Raise / Civil - Shiroi Scope / Thuraipakkam ] | Premkumar
DRA Trinity | to deliver the str & panels to site | Manivel | Closed | 2026-03-10 05:30 | [ 28/02/2026 - Vikram , 550Wp , 64 Nos Delivered to site by Sathyaraj & 6 Labours ] / [ 28/02/2026 - Revised design sent to Danaskeran them via WhatsApp by Manivel for design confirmation ] / [ 03/03/2026 - Design confirmation got and structure order placed with green field ] / [ 10/03/2026 - Structure Materials delivered to site from green filed by Mohan with two labour ] | Mohan
National School | Project details | Premkumar | Closed | 2026-03-03 05:30 | [ 15 KWp / 12 KW AC , On Grid , Non DCR / Mini Rails / CEIG - Client Scope / 9486767757 / Krishnamurthy HM ] | Premkumar
Mr Sivasankar Home | Project details | Premkumar | Closed | 2026-03-04 05:30 | [ 3 KWp / 3.3 KW AC / ON Grid / DCR / Adani - 600 Wp - 5 Nos / Deye / Civil & LA - Shiroi Scope / Anna Nagar / 9789986210 / https://maps.app.goo.gl/Qk75L4NHhEce1eKs9 ] | Premkumar
Ekana Cottage | Complete the electrical work | Manikandan sirkali | Closed | 2026-03-03 05:30 | [ 03/03/2026 - Complete Electrical work has been done by contractor Sriram including final termination ] | Manikandan Sirkali
Mr Sivasankar Home | to complete the str & panel installation | Manivel | Closed | 2026-03-06 05:30 | [ 06/03/2026 - Panels delivered to site by Manikandan & structure work completed by Rajesh Welder ] | Manivel
Shankaran - Shree Viruksha | to done the panel dismantling & re installation | Manivel | Closed | 2026-01-09 05:30 | Structure & Panel installation work Completed by Rajesh Welder | Manivel
Mr Parasuraman 2 | Project details | Premkumar | Closed | 2026-03-09 05:30 | [ 3.6 KWp * 2 Nos / Adani / 600 Wp *12 Nos / Deye 3.3 KW *2 Nos / LA & Civil - Shiroi Scope / https://maps.app.goo.gl/8qhtawt1WVroogg9A / 9710401371 / Parasuraman ] | Premkumar
Alamelu & Arvind | Project details | Premkumar | Closed | 2026-03-10 05:30 | [ Aravind Alamelu / 99401 79029 / 620 Wp * 16 Nos = 9.9 KWp Adani Panel Non DCR / 8 KWp on grid Polycab inverter / Elevated / Civil work - Shiroi Scope / Earthing - 2 Nos ] / [ https://maps.app.goo.gl/oA6kTNhkkzXgYUic9 ] | Premkumar
SPDPL Luz Avenue | to complete the system commissioning | Manikandan | Closed | 2026-03-10 05:30 | [ 09/03/2026 - Net Meter installed at site ] / [ 10/03/2026 - Final termination and system commissioning has been done by Manikandan A & Manikandan ] | Manikandan
M/s Geetha Kalyan | to complete system commissioning & demo | Manikandan | Closed | 2026-03-11 05:30 | [ 11/03/2026 - System commissioning has been done by Manikandan and the system is working within operating limits ] | Manikandan
Mr Solai Ayyar | Project details | Premkumar | Closed | 2026-03-14 05:30 | [ https://maps.app.goo.gl/5BWb6KDibeNwRTbW8 / Mr Solai Ayyar / 9884797847 / 5 KWp & 4 KWp [ 5 KW AC Three Phase & 4 KW Ac Single Phase - Deye Make / Premier / 600 Wp * 16 Nos / DCR & On Grid / GI / Elevated Civil & LA : Shiroi Scope / Rama Puram ] | Premkumar
Mr Sundar | to replace the indication lamp at the ACDB side | Anbarasan | Closed | 2026-03-14 05:30 | indication lamp replaced and the system is working within the operating limits | Anbarasan
Alamelu & Arvind | to complete the str & panel installation | Manivel | Closed | 2026-03-17 05:30 | [ 14/03/2026 - Str and panels delivered to site vy Lourduraj ] / [ 16/03/2026 & 17/03/2026 - Structure installation and panel installation done by Lourduraj ] | Manivel
Alamelu & Arvind | to complete the electrical work | Manikadan & A Manikandan | Closed | 2026-03-17 05:30 | [ 16/03/2026 & 17/03/2026 - Electrical materials delivered to site and completed the installation by Manikandan & A Manikandan ] | Manikandan & A Manikandan
Mr Sairam | Project details | Manivel | Closed | 2025-05-30 05:30 | [Mr Sairam / 5 kWp / 9841473488 / On grid / Low raise / DCR / Anna Nagar / Renew/550Wp/9Nos / DEYE/5 KW/Three Phase ] | Manivel
Mr Pradip Jasiwal | Project details | Premkumar | Closed | 2026-03-18 05:30 | [ 8.6 KWp / 2*4 KW AC / Adani / 620 Wp *14 Nos / Havells *2 Nos / On Grid / Elevated / DCR / LA & Civil - Shiroi Scope / Mr Amit / 98412 59225 / https://maps.app.goo.gl/WZFscTyJonH35TVv5 ] | Premkumar
Ramaniyam Premasaraswathi | Project details | Premkumar | Closed | 2026-03-18 05:30 | [ Mr Natarajan / 9841269164 / 6.6 KWp / Deye - 6 KW AC / 550 Wp * 12 Nos / Mylapore ] | Premkumar
Chettinad Grinding Unit | to get design confirmation & site visit for bill of items | Manivel | Closed | 2026-03-23 05:30 | [ 07/03/2026 - Drawing received from them ] / [19/03/2026 - Module layout and sectional view design sent to them ] / [ 20/03/2026 - Spoke with him for get an appointment ] | Manivel
Mr Solai Ayyar | to complete the str & panel installation | Manivel | Closed | 2026-03-19 05:30 | 16/03/2026 - Panels delivered to site by Sathyaraj & structure delivered by Mr Rajesh , 18/03/2026 - Structure post erection done by Rajesh welder , 19/03/2026 - Panel shifting , Structure installation and panel installation done by Mr Rajesh Welder | Manivel
Mr Mithil & Karan | to complete the site visit and check the feasibility for structure installation | Manivel | Closed | 2026-03-17 05:30 | Site visit and discussion done with client to implement the 16 KWp solar system, advance Cheque collected from them | Manivel
Ceebros boulevard | to get a BG | Manivel | Closed | 2026-03-19 05:30 | BG received from them | Manivel
Mr Mithil & Karan | to get design confirmation & site visit for bill of items | Manivel | Closed | 2026-03-21 05:30 | [ 20/03/2026 - Revised Module Layout sent to karan to get a design confirmation by Manivel ] / | Manivel
DRA Trinity | to complete the str installation | Anbarasan | Closed | 2026-03-20 05:30 | [ 18/03/2026 - Structure shifting work done by Anbarasan & Manikandan A with two labour ] / [ 19/03/2026 - 7 table Structure installation work done by Anbarasan & Manikandan, Manikandan A ] / [ 20/03/2026 - Balance three table structure installation done by Manikandan A, Manikandan, Mohan, Anbarasan ] | Anbarasan
DRA Trinity | to complete the civil Work | Sathyaraj | Closed | 2026-03-23 05:30 | civil work completed by sathayaj | Sathyaraj
Mr Solai Ayyar | complete the civil work | Sathyaraj | Closed | 2026-03-21 05:30 | [ 20/03/2026 - Civil Materials delivered to site and shifted to terrace ] / Civil Work done | Sathyaraj
Mr Solai Ayyar | to complete the electrical work | Manikadan & A Manikandan | Closed | 2026-03-21 05:30 | Electrical work done | Manikandan & Manikandan A
Mr Raja grn gopal street | to complete the electrical work | Manikandan | Closed | 2026-03-02 05:30 | [ Complete electrical work and LA done by Manikandan , Manikandan A, the system is ready to commissioning ] | Manikandan & Manikandan A
Geeyam Prasang | to done system commissioning | Manivel | Closed | 2026-03-21 05:30 | Net Meter installed at site & System Commissioning done on 21/03/2026 by Manivel | Manivel
Mr Pradip Jasiwal | to be done final system commissioning | Manikandan | Closed | 2026-04-25 05:30 | 25th April 2026 - System Commissioning has been done by Manikandan | Manikandan
National School | to complete the sys installation | Manivel | Closed | 2026-04-23 05:30 | [ 17/04/2026 - 23/04/2026 - Structure , Panel , Electrical work completed by Mr Rajesh Contractor ] | Manivel
Shoba Silks Pvt Ltd | to complete the CEIG Process | Manivel | Open | 2026-06-10 05:30
Lancor Ananda | to complete the electrical work | Manikandan | Open | 2026-04-27 05:30 | [ 09/04/2026 - Electrical Materials delivered to site and started installation ] / [ 10/04/2026 - Complete wiring has been done , except Inverter installation ] / Yet to deliver the inverter to site | Manikandan & Manikandan A
Ramaniyam Ashok Vihar | Project details | Manikandan | Closed | 2026-04-25 05:30 | [ 7.7 KWp / NON DCR / GI Low Raise / On Grid / 8 KW Deye Inverter / Ashok Nagar / Arun Balaji - 9840313335 ] | Manivel
Ramaniyam Ashok Vihar | to complete structure & panel installation | Manikandan | Open | 2026-04-28 05:30 | [ 26/04/2026 - Structure & Panels, Electrical Materials are delivered to site by Manikandan & Mohan ] / [ 27/04/2026 - Inverter, DCDB, ACDB & Structure installation done by Manikandan & Manikandan A with two Labour ]
Ramaniyam Radika | Project details | Manivel | Closed | 2026-04-27 05:30 | [ 4.4 KWp , 550 Wp - 8 Nos , Non DCR , GI Low Raise / 4 KW - Single Phase , Deye / Kilpauk / Mr Prabhu - 7299925959 / Mr Palanivel - 8610648821 ] | Manivel
Ramaniyam Akshayam | to visit the site and check the design feasibility , Bill of items | Anbarasan | Closed | 2026-04-27 05:30 | [ 21/04/2026 - Site Visit done By Anbarasan & got design confirmation ] / [ 27/04/2026 - Bill of items received ] | Anbarasan
Ramaniyam Radika | to visit the site and check the design feasibility , Bill of items | Anbarasan | Closed | 2026-04-27 05:30 | [ 27/04/2026 - Site Visit & design confirmation got by Anbarasan ] | Anbarasan
Ramaniyam Akshayam | to deliver the str & panels to site | Anbarasan & Manikandan A | Closed | 2026-05-06 05:30 | 6th May 2026 - Structure Materials are delivered to site by Anbarasan & Mohan | Anbarasan & Manikandan A
Mr Pradheep Boopathy | Wi Fi configuration | Manivel | Closed | 2026-05-02 05:30 | [ Pradheepsolar, Solar@123 ] . Polycab Inverter | Manivel
M/s Deepa Balaji | Project details | Anbarasan & Manikandan | Closed | 2026-04-20 05:30 | [ 620 Wp * 5 Nos , DCR , GI Elevated , 3 KWp Polycab Inverter, Adyar, LA & Civil - Shiroi Scope , Mr Balaji / 9962090556 ] | Anbarasan & Manikandan
Mr Murali | Project details | Premkumar | Closed | 2026-05-06 05:30 | [ Client Name : Mr Murali System Size : 4.8 KWp DC / 5 KW AC Panel Make & Qty : Adani / 600 Wp / 8 Nos Inverter Make & Qty : Deye / Three Phase / 5 KW Type of System : DCR Type of Mountings : GI Elevated No of Earthing's : 2 Sets LA : Shiroi Scope Civil : Shiroi Scope Contact No : 79040 14743 Complete Address :12/266, Parvati Apartments, Ella Rajamanickam Street, Pammal , Chennai - 74 / Map Link - https://maps.app.goo.gl/h3QAGm5bUEfh3Rnf6 ] | Premkumar
Ramaniyam Radika | to complete the str & panel installation | Anbarasan & Manikandan A | Closed | 2026-05-07 05:30 | [ 06/05/2026 - Structure & Panels are delivered to site by Anbarasan & Mohan ] / [ 07/05/2026 - Structure , Panels Shifting & installation done by Anbarasan , Manikandan A with two labour ] | Anbarasan & Manikandan A
Syed Mubarak | to complete the electrical work | Manikandan & Mohan | Closed | 2026-05-07 05:30 | [ 11/03/2026 - DC wiring & earth work completed by Manikandan & Mohan ] / [ 07/05/2026 - Inverter ,ACDB & DCDB delivered to site and installation was done including its termination, Pending is final terminations ] | Manikandan & Mohan
Syed Mubarak | to complete final terminations | Manikandan | Open | 2026-05-08 05:30 | [ Waiting for Meter installation ]
Ramaniyam Radika | to complete the electrical work | Anbarasan & Manikandan A | Closed | 2026-06-05 05:30 | 9th May - Electrical Materials are delivered to site and completed DC Wiring work / 5th June - Final termination and earth wiring work done | Manikandan & Manikandan A
Shoba Silks Pvt Ltd | to complete generation meter installation and terminations | Manivel | Closed | 2026-05-13 05:30 | 9th April 2026 - Generation meter panel delivered to site by Sathyaraj / 13th May 2026 - Generation Meter installed at site and Completed the final terminations by Sriram contractor | Manivel
Mr Murali | to complete the str & panel installation | Manikandan & Mohan | Closed | 2026-05-09 05:30 | 8th April 2026- Structure Materials are delivered to site and started installation , Panels are delivered to site, 9th April 2026 structure & panels installation done by Mr Rajesh | Manikandan & Mohan
Mr Murali | to complete the electrical work | Manikandan & Mohan | Closed | 2026-05-11 05:30 | 9th April 2026 electrical materials are delivered to site and inverter installation and ac wiring done by Manikandan & Mohan, 11th April 2026 - All electrical work done by Manikandan & Mohan | Manikandan & Mohan
Chettinad Grinding Unit | to dispatch materials to site | Manivel | Closed | 2026-05-18 05:30 | 9th May - Discussed with client and get approval to proceed further / 12th May - Bill of items prepared and asked to proceed procurement / 14th May - Structure Order placed with Thanigai / 15th May 2026 - Panels are received and unloaded at office / 16th May 2026 - Complete electrical materials dispatched to site from Shiroi Office / 18th May - Materials are delivered to site | Manivel
Ramaniyam Lakshmi | to place the structure order | Manivel | Closed | 2026-05-15 05:30 | 14th May - Structure enquiry Placed with green field by Manivel / 15th May 2026 - Structure order Placed with green Field | Manivel
Mr Sri Kumar | to complete the site visit along with welder | Manivel | Closed | 2026-05-16 05:30 | 14th May 2026 - Site Visit and design discussion done with fabricator and client by Manivel / 15th May 2026 - revised and final design sent to client to get confirmation by Manivel / 16th May - Got design confirmation | Manivel
Ramaniyam Nivasam | to complete inverter installation | Manikandan | Closed | 2025-12-30 05:30 | 30th Dec 2025 - Inverter delivered to site and done the terminations | Manikandan
Ramaniyam Nivasam | to be done system commissioning | Manikandan | Closed | 2026-04-20 05:30 | 18th April 2026 - Net Meter installed at site / 20th April 2026 - System Commissioning and demo done | Anbarasan
Navins Starwood Towers Phase III | to send design and get conformation | Manivel | Closed | 2026-05-16 05:30 | Got confirmation | Manivel
Dra Downtown | to get design confirmation | Manivel | Closed | 2026-04-28 05:30 | 20th April 2026 - Design sent to them via mail / 28th April 2026 - got design confirmation | Manivel
Dra Downtown | to place structure order and delivery the same to site | Manivel | Closed | 2026-05-12 05:30 | 29th April 2026 - Structure order placed with green field / 12th Amy 2026 - Structure Materials delivered to site and unloaded by sarthyaraj | Manivel
Dra Downtown | to deliver the panels to site | Kesavamoorthy | Closed | 2026-05-13 05:30 | 12th May 2026 - 40 Nos of Panels delivered to site and unloaded by Sathyaraj / 13th May 2026 - 80 No of Panels delivered to site and unloaded by Sathyaraj | Kesavamoorthy
Dra Downtown | to complete structure & panel installation | Sathyaraj | Closed | 2026-05-18 05:30 | 12th May 2026 - Structure received at site and 40 Nos of panels unloaded at site with 3 Labours / 13th May 2026 - Structure Materials shifted to terrace and remaining 80 Panels unloaded at site with 3 Labours / 14th May 2026 - Structure installed for 60 No of solar panels with 3 Labours [ Manikandan & Mohan ] / 15th May - 60 No of Panels fixed 3 Labours [ Mohan & Sathyaraj ] / 16th May - Structure shifted to terrace for remaining 60 Nos with 3 labours / 17th May - Structure installed for the second table /18th May - rest of panel installation done, Completed structure & panel installation | Sathyaraj
Ramaniyam Akshayam | to complete the str & panel installation | Anbarasan & Manikandan A | Closed | 2026-05-08 05:30 | 8th May 2026 - Structure & panel installation done | Anbarasan & Manikandan A
Ramaniyam Akshayam | to complete the electrical work | Anbarasan | Closed | 2026-05-15 05:30 | 13th May 2026 - Electrical Materials are delivered to site and DC, AC cabling work done / 14th May 2026 - Inverter installation and earth cable laying work done / 15th May 2026 - Each cable and final termination done | Anbarasan & Manikandan A
Shoba Silks Pvt Ltd | to submit letter to SE office about work completion | Manivel | Open | 2026-06-11 05:30
Ramaniyam Lakshmi | to deliver the structure to site | Manivel | Open | 2026-05-18 05:30
Krishna Ekta | to complete the str & panel installation | Manikandan | Closed | 2025-10-15 05:30 | Structure & Panel installation work Completed | Manikandan
Krishna Ekta | to visit the site and bill of items | Anbarasan | Closed | 2026-05-16 05:30 | 16th May 2026 - Site Visit done by Anbarasan for bill of items | Anbarasan
Sri krishna Sweets Factory | to complete the final termination at the MV Panel side | Manivel | Closed | 2026-05-18 05:30 | Final termination done | Manivel
Sri krishna Sweets Factory | yet to submit work completion letter to SE office | Manivel | Closed | 2026-05-18 05:30 | 18th May - Work Completion letter sent to Mr Muthu Raman to get signature, the same as well as submitted with SE office by Mr Muthu Raman | Manivel
Krishna Ekta | to deliver the electrical items to site | Manivel | Open | 2026-05-19 05:30
Chettinad Grinding Unit | to complete the str & panel installation | Manivel | Open | 2026-05-19 05:30
Chettinad Grinding Unit | to complete the electrical work | Manivel | Open | 2026-05-19 05:30 | 18th May - Inverter, DC, ACDB installation done by Thanigai team | Manivel
Ceebros boulevard | to visit site to check feasibility for Phase II | Manivel | Closed | 2026-05-19 05:30 | Site visit done and discussed with KR about existing system ROI and Phase II feasibility | Manivel
S&P The Address | to send handover report | Manivel | Closed | 2026-05-19 05:30 | Handover report Softcopy sent to Srinivasan via mail | Manivel
Mr Sri Kumar | to complete structure & panel installation | Manikandan | Closed | 2026-05-23 05:30 | 21st May - Structure & Panels delivered to site / 22nd May - Panels and structures are shifted to terrace | Manivel
Mr Sri Kumar | to complete earth pit installation work | Manikandan | Closed | 2026-05-22 05:30 | 22nd May - Earth pit delivered to site and completed the installation by Manikandan & Mohan | Manikandan & Mohan
Adroit Prosper D Block | to deliver the panels to site and complete the installation | Anbarasan | Open | 2026-05-24 05:30
DRA Trinity | to complete the panel installation | Manivel | Closed | 2026-06-08 05:30 | Panel installation done | Anbarasan & Sathyaraj
Mr Srinivasan Adyar | to complete the electrical work | Manikandan | Closed | 2026-05-14 05:30 | 13th May - Electrical materials delivered to site and started installation, 14th May - Electrical work done, except battery and final termination | Manikandan & Mohan
Mr Srinivasan Adyar | to complete the final termination | Manivel | Open | 2026-05-26 05:30
Mr Srinivasan Adyar | to deliver the Battery to site and complete the installation | Manivel | Open | 2026-05-26 05:30
BCPL Anusham | to complete site visit | Manivel | Closed | 2026-06-01 05:30 | site visit and design confirmation got | Manivel
BCPL Anusham | to complete structure installation | Manivel | Open | 2026-06-04 05:30 | 2nd June - Structure Materials delivered to site by Lourduraj / 3rd June - Structure Materials shifted to terrace by Lourduraj
DRA Skylanties | to delivery the rest of electrical materials to site | Anbarasan | Closed | 2026-06-01 05:30 | Complete electrical items delivered to site [ Anbarasan & Mohan with two labours ] | Anbarasan
DRA Skylanties | to complete site visit to discuss with PM for electrical routings | Manivel | Closed | 2026-06-03 05:30 | site meeting done along with contractor Sriram , complete cable routings are discussed with PM | Manivel
DRA Skylanties | yet to get confirm inverter location from Project Manager | Manivel | Open | 2026-06-04 05:30
Rakshas Enterprises | to complete the relocation of meter panel -client scope | Manivel | Open | 2026-06-04 05:30 | 22nd May - went AD office to get confirmation for meter panel relocation
Mr Murali | to complete the sys commissioning | Manikandan | Closed | 2026-06-04 05:30 | system commissioning and demo completed | Manikandan
M/s Jayanthi | site visit | Manivel | Closed | 2026-06-02 05:30 | Site Visit done for discuss with her about complete hybrid setup | Manivel
M/s Jayanthi | site visit | Manivel | Closed | 2026-06-04 05:30 | Site visit done to check each Phase load Analysis along with their electrical person | Manivel
M/s Jayanthi | Material Procurement | Manivel | Closed | 2026-06-04 05:30 | Discussed with deye team and finalize the order for 5 KW Single phase inverter and 10 KWh battery Wall mount | Manivel
DRA Infinique | to deliver panels to site | Manivel | Open | 2026-06-08 05:30
Ramaniyam Rangavilasam | to complete the sys commissioning | Manikandan | Closed | 2026-06-08 05:30 | System commissioned | Manikandan
DRA Trinity | to complete the electrical work | Manivel | Open | 2026-06-12 05:30
Newry Adora | to delivery the electrical materials to site | Manivel | Open | 2026-06-09 05:30
Sri krishna Sweets Factory | to done system commissioning | Manivel | Closed | 2026-06-09 05:30 | System commissioning done | Anbarasan
Sri krishna Sweets Factory | yet to configure aggregator unit | Anbarasan | Open | 2026-06-10 05:30
Navins Starwood Towers Phase III | to complete structure installation | Manivel | Open | 2026-06-12 05:30

## Project details
Project Name | Client Name | Mobile No | Mail ID | Shipping Address | Billing Address | Google Maps | Sys Size | Category | Mounting Types | Type of Sys | Panel Make & Qty | Inverter Make & Qty | Cable Make | LA Scope | Civil Scope | TNEB Scope | CEIG Scope
Mahameru | Green valley | 9444059787 | vel@gmail,com | Adyar, Chennai | Adyar, Chennai |  | 10 KWp | On Grid | GI Elevated | NDCR | 610 & 18 Nos | Deye , 10 KW , On grid | Polycab | Shiroi | Shiroi | Shiroi | Shiroi
Mr Pradheep Boopathy | Mr Pradheep Boopathy | 9444059787 |  | Chennai | Chennai |  | 3 | On Grid | GI Elevated | DCR | Adani | Dye | Polycab |  | Shiroi | Shiroi | Shiroi
Mr Murali | Mr Murali | 7904014743 | Nil | 16, Parvati Apartments, Ella Rajamanickam Street, Pammal, Chennai - 600074 | 16, Parvati Apartments, Ella Rajamanickam Street, Pammal, Chennai - 600074 | https://maps.app.goo.gl/B5oVPz3nfqGFCFcU6 | 4.8 KWp | On Grid | GI Elevated | DCR | Adani /620 /8 Nos | Deye / 6KW / Three Phase / On grid | Polycab | Shiroi | Shiroi | Shiroi | Shiroi
Ramaniyam Lakshmi | Ramaniyam Realtors LLP | 9952919566 | Nil | Chennai | Adyar | Nil | 4.4 | On Grid | RCC Low Raise | NDCR | 555 Wp / 8 Nos | Deye / 4 KW / Single Phase | Polycab | Client | Shiroi | Shiroi | Client
Navins Starwood Towers Phase III | Navin Housing and Properties Private Ltd | 9965982275 | Purchase@navins.in | Navins Starwood Towers Phase III Mambakkam - Medavakkam Main Rd, Vengavasal, Chennai, Tamil Nadu 600126 Site Contact: 8754580105 / 9487391687 Contact Person: Mr. Thangaraj / Mr. Rajakumar | NAVIN HOUSING AND PROPERTIES (P) LTD Corp Off: Navins Triumph NEW NO 804 AND 802, ANNA SALAI, NANDANAM, CHENNAI, TAMIL NADU, 600035 GST No: 33AAACN9269M1ZY PAN No: AAACN9269M | https://maps.app.goo.gl/xudana92YAW9vNRdA | 36 | On Grid | RCC Low Raise | NDCR | Adani / Waaree / 600 / 60 Nos | Deye / 40 KW / Three Phase | Polycab | Client | Client | Client | Client
Dra Downtown | M/s. Chennai Premium projects Pvt Ltd | 7305021588 | Nil
Ramaniyam Akshayam | Ramaniyam Realtors LLP | Mr Sridhar / 9841072889 | Nil |  |  | https://maps.app.goo.gl/c6wS6b9ZcwRuBJd3A | 5.5 | On Grid | RCC / GI Low Raise | NDCR | Renew / 590 Wp /10 Nos | 6 KW / Deye/ Three Phase | Polycab | Client | Client | Shiroi | Client
M/s Deepa Balaji | M/s Deepa Balaji | [6 empty] | On Grid | RCC / GI Elevated | DCR |  |  |  | Shiroi | Shiroi | Shiroi | Not Applicable
Krishna Ekta | Krishna Group | 9677228304 / Prasath | Nil |  |  | https://maps.app.goo.gl/6frbBzJMd31v1uV3A | 3.3 | On Grid | RCC / GI Low Raise | NDCR | Axitec / 550 Wp / 6 Nos |  |  | Client | Client | Shiroi | Not Applicable
M/s Jayanthi | M/s Jayanthi | 9840798872 | Nil | 32nd Cross Street, Besant Nagar, Chennai - 600090 | 32nd Cross Street, Besant Nagar, Chennai - 600090 | https://maps.app.goo.gl/a9FXmmvfVpTwD46t8 | 5 | Hybrid | RCC / GI Elevated | DCR | Waaree / 600 Wp / 8 Nos | 5 KW / Polycab / Three Phase | Polycab | Shiroi | Shiroi | Shiroi | Not Applicable
Mr Swaminathan | Mr Swaminathan | 94434 91391 |  | T Nagar | T Nagar | https://maps.app.goo.gl/nr21graFQKehvPih9 | 2*3 KWp | On Grid | RCC / GI Elevated | DCR | Adani / Vikram | Deye / 3.3 KW *2 Nos / Single Phase | Polycab | Shiroi | Shiroi | Shiroi | Not Applicable
Mr.Rajan Babu | Mr.Rajan Babu | 9677298275 | Nil | Neelankarai | Neelankarai | https://maps.app.goo.gl/PU295WVtwEvxCRHSA | 3.3 * 2 Nos | On Grid | RCC / GI Elevated | DCR |  |  |  | Shiroi | Shiroi | Shiroi | Not Applicable
M/s Uma Maheshwari | M/s Uma Maheshwari | 9962547616 | Nil | Kolathur | Kolathur | https://maps.app.goo.gl/XdSob6JbdHqrxJ949 | 5 | On Grid | RCC / GI Elevated | DCR | 600 Wp / 8 Nos / Adani | Deye / 5 KWp / Three Phase | Polycab | Shiroi | Shiroi | Shiroi | Not Applicable
M/s V J Saraswathi | M/s V J Saraswathi | 9444853679 | Nil | 11/6 Krishnaswamy st, Abiramapuram , Chennai 18 | 11/6 Krishnaswamy st, Abiramapuram , Chennai 18 | https://maps.app.goo.gl/QFXDJRuagZnYm1gn6 | 3 | On Grid | RCC / GI Elevated | DCR | Adani / 600 Wp / 5 Nos | Deye / 3.3 KW / Single phase | Polycab | Shiroi | Shiroi | Shiroi | Not Applicable
Mr Sri Kumar | Mr Sri Kumar | 9841826973 | Nil | Ashok Nagar | Ashok Nagar | https://maps.app.goo.gl/gKb6QtSH52Gm1hsd8 | 11 KWp [ 4.2 * 2 Nos , 2.2 *1 Nos ] | On Grid | RCC / GI Elevated | DCR | Premier / 610 Wp / 18 Nos | Deye - [ 5 KW * 2 Nos - Three Phase , 3.3 KW *1 No - Single phase ] | Polycab | Shiroi | Shiroi | Shiroi | Not Applicable
BCPL Anusham
BCPL Anusham / Arjun Prasath
BCPL Anusham / Dhandapani
BCPL Anusham / Ramesh
BCPL Anusham / Sri Bala
DRA Infinique | DRA | [5 empty] | 20 KWp | On Grid | RCC / GI Low Raise | NDCR | 620 Wp Vikram / 29 Nos | Deye & 20 KW | Polycab | Client | Shiroi | Client | Client
Sri krishna Sweets Factory | Sri Krishna Sweets Factory |  |  | Coimbatore | Coimbatore |  | 100 kWp | On Grid | GI Metal Sheet / Long Rails | NDCR | 550 Wp | 100 KW / Goodwe | Polycab | Shiroi | Shiroi | Shiroi | Shiroi

## Budgets
No | Project Name | Size | Status | Project Cost | Actual Cost | Est Profit | Act Profit | Year | Profit In rs
1 | BBCL Midland | 50 | Completed | 0 | 0 | 0% | 0% | 2022 | 0
2 | Zebronics | 9.9 | Completed |  |  |  |  | 2023
3 | Dr Sivabalan |  | Completed |  |  |  |  | 2024
4 | Indus Allaiance | 2 | Completed |  |  |  |  | 2024
5 | Mr Srinivasan | 9.8 | Completed |  |  |  |  | 2024
6 | Ramaniyam Subham | 2.2 | Completed |  |  |  |  | 2024
7 | Ramaniyam Sasta | 3.3 | Completed |  |  |  |  | 2024
8 | Ramaniya Syndicate | 5.4 | Completed |  |  |  |  | 2024
9 | DRA Homes | 25 | Completed |  |  |  |  | 2024
10 | Mr Rajesh | 10 | Completed |  |  |  |  | 2024
11 | Dr Sridhar | 7 | Completed |  |  |  |  | 2024
12 | Mr Varun | 4.32 | Completed |  |  |  |  | 2024
13 | Mr Muthu | 10 | Completed |  |  |  |  | 2024
14 | Lancor TCP Altura | 20 | Completed |  |  |  |  | 2024
15 | Sribalaji Lancor | 4.69 | Completed |  |  |  |  | 2024
16 | L&T | 7.7 | Completed |  |  |  |  | 2024
17 | Navins Hanging Garden | 25.85 | Completed |  |  |  |  | 2024
18 | Ramaniyam Senate | 6.6 | Completed |  |  |  |  | 2024
19 | Ramaniyam Kalpataru | 3.2 | Completed |  |  |  |  | 2024
20 | SSBPL KS Avanue | 4 | Completed |  |  |  |  | 2024
21 | Chettinad Hospital | 60 | Completed |  |  |  |  | 2024
22 | Hari Shree Senior School | 81 | Completed |  |  |  |  | 2024
23 | Hari Shree Junior School | 9.9 | Completed |  |  |  |  | 2024
24 | Ceebros boulevard | 82 | Completed |  |  |  |  | 2024
25 | Radiance Flourish | 240 | Completed | 9083344 | 7999931.4 | 10% | 11.93% | 2024 | 1083412.6
26 | Enexio Fill Factory | 95.6 | Completed | 4703752 | 4049053.548 | 15% | 13.92% | 2024 | 654698.4522
27 | Abirami Eng Cons & Co | 20 | Meter Client Scope |  |  |  |  | 2024
28 | Mr Karthikeyan / TVS Hamlet | 6 | Completed |  |  |  |  | 2024
29 | RWD Grand Corridor | 75 | Completed | 3727996 | 2771837.181 | 20% | 25.65% | 2024 | 956158.8192
30 | Jains Anarghya | 19 | Meter Client Scope |  |  |  |  | 2024
31 | Jains Aadheeswar | 42 | Meter Client Scope |  |  |  |  | 2024
32 | Jains Advaya | 64 | Holding from Shiroi |  |  |  |  | 2024
33 | Mr Rathinam | 5 | Completed |  |  |  |  | 2024
34 | Mr Anandan | 4 | Completed | 240000 | 202105.4 | 10% | 15.79% | 2024 | 37894.6
35 | Ramaniyam Summit | 3.3 | Completed |  |  |  |  | 2024
36 | Ramaniyam Trinity | 5.5 | Completed |  |  |  |  | 2024
37 | Mr Kannaiyan | 2.2 | Completed |  |  |  |  | 2024
38 | Mr AM Raja | 3.4 | Completed |  |  |  |  | 2024
39 | Mr Krishnamurthy | 2 | Completed |  |  |  |  | 2024
40 | GRN Kuyili | 2 | Completed |  |  |  |  | 2024
41 | Geeyam Meenakshi Illam | 4 | Completed |  |  |  |  | 2024
42 | GK Shetty tulive Bellevue | 44 | Completed | 1916814 | 1518939.041 | 10% | 20.76% | 2024 | 397874.9588
43 | Mr Swaminathan | 3.2 | Completed |  |  |  |  | 2024
44 | Prestige Hill Crest | 135 | Waiting for Net Meter | 8967231 | 4492644.93 | 10% | 49.9% | 2024 | 4474586.07
45 | Sheela Green | 13.5 | Completed | 774591 | 706110.8096 | 10% | 8.841% | 2024 | 68480.1904
46 | Navins Starwood | 36 | Completed | 1795000 | 1224746.98 | 15% | 31.77% | 2024 | 570253.02
47 | Shree Vrikshah homes | 9.9 | Completed | 390000 | 248761.1 | 10% | 36.22% | 2024 | 141238.9
48 | Legendry Builders | 9.9 | Completed | 450000 | 302420.078 | 10% | 32.8% | 2024 | 147579.922
49 | Mr Srinivasan L&T | 5 | Completed |  |  |  |  | 2024
50 | Khurinji's Iris | 3 | Completed |  |  |  |  | 2024
51 | Hindu School Payalwar Street | 110 | Completed | 7532270 | 5496751.228 | 15% | 27.02% | 2024 | 2035518.772
52 | Adroit Prosper | 10 | Completed | 501199 | 366961.42 | 7.5% | 26.78% | 2024 | 134237.58
53 | RCC e Constrcution | 20 | Completed | 649621 | 462975.4 | 10% | 28.73% | 2024 | 186645.6
54 | Mr Saravana Bhava | 2 | Completed |  |  |  |  | 2024
55 | Mr Srinivasan Madipakkam | 2 | Completed |  |  |  |  | 2024
56 | Ramaniyam Parampara | 3.3 | Completed |  |  |  |  | 2024
57 | Mr Ravish | 3.5 | Completed |  |  |  |  | 2024
58 | GRN Shree Nivas | 2 | Completed |  |  |  |  | 2024
59 | GRN Mangaladev | 2 | Completed |  |  |  |  | 2024
60 | Mr Bharath | 5 | Completed |  |  |  |  | 2024
61 | Mr.Anilkumar Mehta - Home | 8.8 | Completed |  |  |  |  | 2024
62 | Opus 96 | 5.9 | Completed |  |  |  |  | 2024
63 | BEEL | 3.3 | Completed |  |  |  |  | 2024
64 | Ramaniyam Padhuka | 2.7 | Completed |  |  |  |  | 2024
65 | DMS | 29 | Holding from client |  |  |  |  | 2024
66 | CM Constrcution | 3.3 | Completed | 235000 | 215595.964 | 10% | 8.257% | 2024 | 19404.036
67 | Mr Muralidharan | 3.3 | Completed |  |  |  |  | 2024
68 | Mr Devadoss | 7 | Completed | 505000 | 347602.93 | 10% | 31.17% | 2024 | 157397.07
69 | Mr Seshadri | 4 | Completed |  |  |  |  | 2024
70 | SLNC | 13.5 | Completed | 877958 | 542179.796 | 10% | 38.25% | 2024 | 335778.204
71 | Mr Lakshmanan | 3.3 | Completed |  |  |  |  | 2024
72 | SSBPL KP Puram | 8 | Completed |  |  |  |  | 2024
73 | Mr Chakrapani | 4.4 | Completed | 255000 | 217981.036 | 10% | 14.52% | 2024 | 37018.964
74 | Lancor Infinys | 20 | Completed | 853575 | 647277.32 | 10% | 24.17% | 2024 | 206297.68
75 | Ramaniyam Adhri | 2.2 | Completed | 169244 | 98761.516 | 10% | 41.65% | 2024 | 70482.484
76 | Mr MV Srinivasan | 13.2 | Completed |  |  |  |  | 2024
77 | Mr Kesav Anand | 2.2 | Completed |  |  |  |  | 2024
78 | Khurinji's Acanthus | 5 | Completed |  |  |  |  | 2024
79 | Shree Niketan | 9 | Completed |  |  |  |  | 2024
80 | Geeyam Nandhini | 4 | Completed |  |  |  |  | 2024
81 | 4 Bricks | 5 | Completed |  |  |  |  | 2024
82 | GRN Bakhavachalam | 2 | Completed |  |  |  |  | 2024
83 | GRN CP Ramasamy | 2 | Completed |  |  |  |  | 2024
84 | Mr Arangarajan | 5 | Completed |  |  |  |  | 2024
85 | Mr C Kumar | 3.2 | Completed |  |  |  |  | 2024
86 | Mr Sangeetha | 5.5 | Completed |  |  |  |  | 2024
87 | Navins Vyakarana | 5 | Completed | 258834 | 193477.132 | 10% | 25.25% | 2024 | 65356.868
88 | Vgk Saiharithik | 5 | Completed | 316000 | 241858.04 | 10% | 23.46% | 2024 | 74141.96
89 | Mr Vigneswaran | 3.3 | Completed |  |  |  |  | 2024
90 | Vinayaga Infratech | 5 | Completed | 255000 | 169133.82 | 10% | 33.67% | 2024 | 85866.18
91 | Mr Ramkumar | 3.3 | Completed |  |  |  |  | 2024
92 | Ms. Sridevi | 3.3 | Completed |  |  |  |  | 2024
93 | Mr Lakshman Raj | 3.3 | Completed |  |  |  |  | 2024
94 | Mr Balaji | 3.3 | Completed |  |  |  |  | 2024
95 | Mr Aatish | 3.3 | Completed |  |  |  |  | 2024
96 | VGK Unity Kingdom | 10 | Completed | 507212 | 370536.8 | 10% | 26.95% | 2024 | 136675.2
97 | VGK Summer Garden | 20 | Completed | 1014424 | 676482.7 | 10% | 33.31% | 2024 | 337941.3
98 | MSM Unit II, Phase III | 250 | Completed | 9562500 | 7351732.925 | 7.5% | 23.12% | 2024 | 2210767.075
99 | Ramaniyam Abinaya | 3.3 | Completed | 192340 | 111685.476 | 10% | 41.93% | 2024 | 80654.524
100 | Rite Choice | 2 | Completed |  |  |  |  | 2024
101 | S&P Courtyard | 30 | On Progress | 1150004 | 1073924.1 | 10% | 6.616% | 2024 | 76079.9
102 | VP Jewellery | 5 | Completed |  |  |  |  | 2024
103 | Mr Chandrasekar | 3 | Completed |  |  |  |  | 2024
104 | SSBPL NBR 2 | 4.4 | Completed | 287233 | 169775.476 | 10% | 40.89% | 2024 | 117457.524
105 | Lancor Hiranmayi | 5 | Completed | 260000 | 188121.86 | 10% | 27.65% | 2024 | 71878.14
106 | Lancor Sahana | 5 | Completed | 260000 | 180425.26 | 10% | 30.61% | 2024 | 79574.74
107 | Lancor Ratirupa | 5 | Meter Client Scope | 260000 | 184514.16 | 10% | 29.03% | 2024 | 75485.84
108 | Lancor Homeleigh | 5 | Completed | 260000 | 186711.56 | 10% | 28.19% | 2024 | 73288.44
109 | Arihanth Nahar | 10 | Completed | 533628 | 374043.82 | 10% | 29.91% | 2024 | 159584.18
110 | Mr Ramaswamy | 3.3 | Completed | 204000 | 133153.512 | 10% | 34.73% | 2024 | 70846.488
111 | Mr Venkateswaran RTO | 7 | Completed | 330000 | 246070.72 | 15% | 25.43% | 2024 | 83929.28
112 | SSBPL West Mambalam | 3.3 | Completed | 146131 | 87434.296 | 10% | 40.17% | 2024 | 58696.704
113 | Kalakchetra | 10 | Waiting for Net Meter | 633504 | 526763.156 | 18% | 16.85% | 2024 | 106740.844
114 | Mr Venkatraman | 9 | Completed | 465000 | 348765.34 | 10% | 25% | 2024 | 116234.66
115 | Ramaniyam Shyamala | 3.3 | Completed | 192340 | 108374.24 | 10% | 43.65% | 2024 | 83965.76
116 | DRA Urbania | 67 | Completed | 2699936 | 2134946.716 | 20% | 20.93% | 2024 | 564989.284
117 | Mr.Sriram Pallikaranai | 4 | Completed | 276615 | 249005.1906 | 10% | 9.981% | 2024 | 27609.8094
118 | Ramaniyam Sri Vaikuntam | 3.3 | Completed | 192338 | 126561.396 | 10% | 34.2% | 2024 | 65776.604
119 | Newry Astor | 10 | Completed | 523876 | 400800.442 | 10% | 23.49% | 2024 | 123075.558
120 | Vaf def Aero Systems | 528 | Completed | 20256400 | 15566528.41 | 20% | 23.15% | 2024 | 4689871.589
121 | Mr Parasuraman | 5 | Completed | 280000 | 277485.912 | 10% | 0.8979% | 2024 | 2514.088
122 | Mr Palanivelan | 3.3 | Completed | 220000 | 192299.808 | 10% | 12.59% | 2024 | 27700.192
123 | SSBPL SPRING SEASON | 3.3 | Completed | 146131 | 85334.56 | 10% | 41.6% | 2024 | 60796.44
124 | Luxebuilt Homes Pvt ltd | 3.3 | Completed | 98931 | 43395.7 | 15% | 56.14% | 2024 | 55535.3
125 | Lancor Lumina H2 | 20 | Meter Client Scope | 799199 | 675807.7 | 15% | 15.44% | 2024 | 123391.3
126 | Felix Johnson | 7.5 | Completed | 376726 | 250895.24 | 10% | 33.4% | 2024 | 125830.76
127 | Mr Elumalai | 3.3 | Completed | 210000 | 163096.8 | 10% | 22.33% | 2024 | 46903.2
128 | Log on infra pvt ltd (NDR) | 22.5 | Completed | 916693 | 597921.364 | 20% | 34.77% | 2024 | 318771.636
129 | M/S Ramya | 10 | Completed | 572000 | 362864.04 | 10% | 36.56% | 2024 | 209135.96
130 | Mr Davidson | 8.7 | Completed | 557499 | 364263.796 | 10% | 34.66% | 2024 | 193235.204
131 | Navins Sankalpa | 8 | Completed | 309999.02 | 244586.36 | 10% | 21.1% | 2024 | 65412.66
132 | Sri Ganapathy Ashram | 14 | Completed | 745000 | 656445.826 | 10% | 11.89% | 2024 | 88554.174
133 | Jains Aura | 3 | Completed | 170200 | 145345.16 | 10% | 14.6% | 2024 | 24854.84
134 | Mr Manokaran | 3 | Completed | 195000 | 171172.38 | 10% | 12.22% | 2025 | 23827.62
135 | Mr Vijay Sabapathy | 10 | Completed | 515435 | 370087.02 | 15% | 28.2% | 2024 | 145347.98
136 | Sri Ganapathy Ashram, Phase II | 9.9 | Completed | 466951 | 302342.32 | 10% | 35.25% | 2024 | 164608.68
137 | Mr Venkatesh | 3.3 | Completed | 185000 | 169981 | 10% | 8.118% | 2025 | 15019
138 | Mr Koildhass | 5 | Completed | 254882 | 183782.96 | 10% | 27.89% | 2025 | 71099.04
139 | Ramaniyam Bharadwaj | 4.4 | Completed | 221805 | 120080.6 | 12% | 45.86% | 2025 | 101724.4
140 | M/s Latha ganesh | 5 | Completed | 350283 | 272299.52 | 10% | 22.26% | 2025 | 77983.48
141 | Ramaniyam Nagas | 3.3 | Completed | 184340 | 105770.616 | 15% | 42.62% | 2025 | 78569.384
142 | Ramaniyam tulsi | 5 | Completed | 307977 | 184759.32 | 10% | 40.01% | 2025 | 123217.68
143 | Ramaniyam Anugraha | 8.8 | Completed | 418861 | 265410.22 | 10% | 36.64% | 2025 | 153450.78
144 | Ramaniyam Ocean dew Block 4 | 8.8 | Completed | 418861 | 253814.608 | 10% | 39.4% | 2025 | 165046.392
145 | Ramaniyam Ocean dew Block 5 | 8.8 | Completed | 425056 | 255520.62 | 10% | 39.89% | 2025 | 169535.38
146 | Ramaniyam Vedha | 3.3 | Completed | 184340 | 102648.396 | 10% | 44.32% | 2025 | 81691.604
147 | Town & Country Project | 0 | Completed | 21240 | 8000 | 10% | 62.34% | 2025 | 13240
148 | Nithya Akshayam | 5.5 | Completed | 323000 | 217251.72 | 10% | 32.74% | 2025 | 105748.28
149 | Mr Vishnu Vijay | 3.3 | Completed | 210926 | 137745.14 | 10% | 34.7% | 2025 | 73180.86
150 | M/s Srividya Srikanth | 3.3 | Completed | 217532 | 164385.1 | 10% | 24.43% | 2025 | 53146.9
151 | Mr Subramanian | 6.6 | Completed | 430000 | 292687.4 | 10% | 31.93% | 2025 | 137312.6
152 | Mr Babu Govindrajan | 3.3 | Completed | 195000 | 151755.26 | 10% | 22.18% | 2025 | 43244.74
153 | Mr Saravanan | 5 | Completed | 251499 | 164932.68 | 10% | 34.42% | 2025 | 86566.32
154 | Mr Sairam | 5 | Completed | 310233 | 241055.04 | 10% | 22.3% | 2025 | 69177.96
155 | Mr Sankaranarayanan | 3.3 | Completed | 195000 | 167824.888 | 10% | 13.94% | 2025 | 27175.112
156 | DRA Skylanties | 19 | On Progress | 774973 | 775289.16 | 15% | -0.0408% | 2025 | -316.16
157 | Mr Venkatesh | 3.3 | Completed | 180000 | 161805.06 | 10% | 10.11% | 2025 | 18194.94
158 | Geeyam Skandha | 4.4 | Completed | 240000 | 139141.598 | 10% | 42.02% | 2025 | 100858.402
159 | Mr Chandran | 4.4 | Completed | 311398 | 245250.02 | 12% | 21.24% | 2025 | 66147.98
160 | Mr Jeyaseelan | 3.3 | Completed | 195000 | 177499.9 | 10% | 8.974% | 2025 | 17500.1
161 | Krishna Ekta | 3.3 | Holding from client | 172957 | 120578.916 | 10% | 30.28% | 2025 | 52378.084
162 | Mr Sriram | 6 | Completed | 315000 | 221235.9 | 10% | 29.77% | 2025 | 93764.1
163 | Mr Venkateshperumal | 3.3 | Completed | 211185 | 165575.16 | 10% | 21.6% | 2025 | 45609.84
164 | Mr. Ramesh Babu | 3.3 | Completed | 190000 | 157642.98 | 10% | 17.03% | 2025 | 32357.02
165 | DRA Optima | 40 | Completed | 1655226 | 1248145.54 | 15% | 24.59% | 2025 | 407080.46
166 | Mr Sanjay | 9.9 | Completed | 585000 | 515082.82 | 15% | 11.95% | 2025 | 69917.18
167 | Mr Ginu Mathew | 3.3 | Completed | 190000 | 164949.6 | 10% | 13.18% | 2025 | 25050.4
168 | Dr Ramesh | 5 | Completed | 324000 | 268951.2 | 10% | 16.99% | 2025 | 55048.8
169 | Ranamaniyam Saranagati | 3.3 | Completed | 184339 | 111923.52 | 10% | 39.28% | 2025 | 72415.48
170 | Pacifica Aurum | 3.3 | Completed | 202838 | 141870.16 | 10% | 30.06% | 2025 | 60967.84
171 | Mr Prabakaran | 3.3 | Completed | 195000 | 180075.02 | 10% | 7.654% | 2025 | 14924.98
172 | RCC e Constrcution 2 | 20 | Meter Client Scope | 328398.64 | 234396.31 | 10% | 28.62% | 2025 | 94002.33
173 | GRN Chakarabani street | 2.2 | Completed | 145000 | 79450.384 | 10% | 45.21% | 2025 | 65549.616
174 | Mr Siva Elango | 5 | Completed | 333000 | 271828.7 | 10% | 18.37% | 2025 | 61171.3
175 | Shoba Silks Pvt Ltd | 100 | Waiting for Net Meter | 3401122 | 2784512.12 | 11% | 18.13% | 2025 | 616609.88
176 | Green Crest | 9.7 | Completed | 387000 | 297131.02 | 10% | 23.22% | 2025 | 89868.98
177 | Mr Shanmugam | 5.5 | Completed | 300000 | 195156.84 | 15% | 34.95% | 2025 | 104843.16
178 | Krishnaveni | 9.3 | Completed | 483562 | 351484.786 | 10% | 27.31% | 2025 | 132077.214
179 | Jyothiswari | 2.2 | Completed | 167790 | 125936.224 | 10% | 24.94% | 2025 | 41853.776
180 | Mr Sivasankar | 2.2 | Completed | 168000 | 117715.86 | 10% | 29.93% | 2025 | 50284.14
181 | Lancor Lumina ABC | 20.5 | Holding from client | 782406 | 671686.7 | 15% | 14.15% | 2025 | 110719.3
182 | Sri krishna Sweets | 20 | Waiting for Net Meter | 998208 | 750629.72 | 15% | 24.8% | 2025 | 247578.28
183 | Mahameru | 10 | Waiting for Net Meter | 387000 | 334954.5 | 10% | 13.45% | 2025 | 52045.5
184 | Jains Seven 77 | 30 | Holding from client | 1168200 | 980838.86 | 15% | 16.04% | 2025 | 187361.14
185 | SPDPL Luz Avenue | 8 | Completed | 374058 | 298422.96 | 10% | 20.22% | 2025 | 75635.04
186 | Jains Aadhidev | 30 | Holding from client | 1168200 | 983307.06 | 15% | 15.83% | 2025 | 184892.94
187 | Mr Arjun Prasath | 9.7 | Completed | 504192 | 391158.78 | 10% | 22.42% | 2025 | 113033.22
188 | Zeneto infra | 3.3 | Waiting for Net Meter | 167165 | 115864.74 | 10% | 30.69% | 2025 | 51300.26
189 | Mr Sridhar Rajan | 6 | Completed | 429217 | 309169.1 | 15% | 27.97% | 2025 | 120047.9
190 | Mr Rangachari | 8 | Completed | 496000 | 368479.92 | 10% | 25.71% | 2025 | 127520.08
191 | Mr.Sukumaran | 3.3 | Completed | 217565 | 159613.005 | 10% | 26.64% | 2025 | 57951.995
192 | Ramaniyam Nivasam | 4.4 | Completed | 221806 | 136826.39 | 10% | 38.31% | 2025 | 84979.61
193 | Hindu School Adyar / Service | 50 | Completed | 422276 | 251381.88 | 10% | 40.47% | 2025 | 170894.12
194 | GRN Ambili Srinivas | 3.3 | Completed | 208993 | 160335.06 | 10% | 23.28% | 2025 | 48657.94
195 | SPDPL Padmalaiya | 4.4 | Completed | 243001 | 155835.97 | 10% | 35.87% | 2025 | 87165.03
196 | Nirupa Properties | 2.2 | Completed | 150000 | 95095.2 | 10% | 36.6% | 2025 | 54904.8
197 | Mr.Karthikeyan / CM Constructions | 4.8 | Completed | 333000 | 289891.18 | 10% | 12.95% | 2025 | 43108.82
198 | Sri krishna Sweets Factory | 100 | On Progress | 550000 | 456880 | 10% | 16.93% | 2025 | 93120
199 | Mr Ravi / Tiruvannamalai | 10 | Completed | 160000 | 110073.2 | 15% | 31.2% | 2025 | 49926.8
200 | Mr.Arunkumar | 3.3 | Completed | 195000 | 179076.26 | 10% | 8.166% | 2025 | 15923.74
201 | Rakshas Enterprises | 10 | Waiting for Net Meter | 500000 | 398427.54 | 12.5% | 20.31% | 2025 | 101572.46
202 | Mr.Anilkumar Mehta - Office | 10.5 | Completed | 683613 | 456060.748 | 10% | 33.29% | 2025 | 227552.252
203 | Mr.Rajan Babu | 6.6 | Completed | 437266 | 332728.88 | 10% | 23.91% | 2025 | 104537.12
204 | Ramaniyam Sankaram | 4.4 | Completed | 224989 | 134826.56 | 10% | 40.07% | 2025 | 90162.44
205 | Mr Raja grn gopal street | 10 | Completed | 770798 | 469616.77 | 10% | 39.07% | 2025 | 301181.23
206 | Mr.Kasinathan | 8.8 | Completed | 568711 | 397141.63 | 10% | 30.17% | 2025 | 171569.37
207 | Newry Adora | 20 | Holding from client | 800788 | 573729 | 15% | 28.35% | 2025 | 227059
208 | Lancor Bagya | 5 | Holding from client | 238958 | 275458.4 | 10% | -15.27% | 2025 | -36500.4
209 | Lancor Ananda | 5 | Waiting for Net Meter | 238958 | 199164.76 | 10% | 16.65% | 2025 | 39793.24
210 | Mr Jeyakumar | 4.8 | Completed | 325000 | 256168.96 | 15% | 21.18% | 2025 | 68831.04
211 | Geeyam Suryakantham | 3.3 | Completed | 161964 | 104770.456 | 10% | 35.31% | 2025 | 57193.544
212 | Geeyam Prasang | 4.4 | Completed | 214916 | 294785.4 | 10% | -37.16% | 2025 | -79869.4
213 | Mr Saravanan 4 Bricks | 3.3 | Waiting for Net Meter | 174990 | 92823.11 | 10% | 46.96% | 2025 | 82166.89
214 | Mr Srinivasan Adyar | 6 | On Progress | 565000 | 516982.1 | 10% | 8.499% | 2025 | 48017.9
215 | Mr Nitin | 6 | Completed | 400000 | 331811.54 | 10% | 17.05% | 2025 | 68188.46
216 | Khurinji's the Orchid | 5 | Completed | 288905 | 209183.15 | 15% | 27.59% | 2025 | 79721.85
217 | Ramaniyam Rangavilasam | 3.3 | Completed | 224989 | 149587.05 | 15% | 33.51% | 2025 | 75401.95
218 | VM Builder | 5 | Completed | 340000 | 264792.32 | 14% | 22.12% | 2025 | 75207.68
219 | Shankaran - Shree Viruksha | 8 | Waiting for Net Meter | 642640 | 454863.3 | 15% | 29.22% | 2025 | 187776.7
220 | Ramaniyam Gayathri | 5.4 | Completed | 274753 | 174912.04 | 15% | 36.34% | 2025 | 99840.96
221 | Ramaniyam Manasa | 9.8 | Waiting for Net Meter | 456419 | 272022.332 | 15% | 40.4% | 2025 | 184396.668
222 | Swarnalatha | 4.3 | Completed | 260000 | 215968.25 | 15% | 16.94% | 2025 | 44031.75
223 | Adroit Prosper D Block | 10 | Holding from client | 387000 | 290077.18 | 10% | 25.04% | 2025 | 96922.82
224 | Mr Sundar | 5.5 | Completed | 337761 | 311925.74 | 10% | 7.649% | 2025 | 25835.26
225 | Accord Foundtaions | 30.42 | On Progress | 1585654 | 1441285.42 | 10% | 9.105% | 2025 | 144368.58
226 | Zirve Project | 30 | Yet to Start | 1129744 | 1476691.85 | 10% | -30.71% | 2025 | -346947.85
227 | Ekana Cottage | 8 | Waiting for Net Meter | 300000 | 254505.05 | 10% | 15.16% | 2025 | 45494.95
228 | Mr Aditya Baskar | 4.2 | Completed | 257000 | 222930.41 | 10% | 13.26% | 2025 | 34069.59
229 | Mr Manickam | 1.2 | Completed | 108862 | 93584.58 | 10% | 14.03% | 2025 | 15277.42
230 | M/s Geetha Kalyan | 1.8 | Completed | 148823 | 121423.68 | 10% | 18.41% | 2025 | 27399.32
231 | Syed Mubarak | 6.3 | Waiting for Net Meter | 310000 | 253601.44 | 8% | 18.19% | 2025 | 56398.56
232 | Mr Vasu rao | 4.2 | Completed | 253000 | 231337.64 | 10% | 8.562% | 2025 | 21662.36
233 | DRA Trinity | 35.2 | On Progress | 1370979 | 1093005.5 | 20% | 20.28% | 2025 | 277973.5
234 | National School | 15 | Waiting for Net Meter | 497182 | 455870.05 | 10% | 8.309% | 2025 | 41311.95
235 | Mr Sivasankar Home | 3 | Completed | 206880 | 164997.57 | 10% | 20.24% | 2025 | 41882.43
236 | Chettinad Grinding Unit | 10 | Waiting for Net Meter | 565220 | 468794.4 | 10% | 17.06% | 2025 | 96425.6
237 | Mr Parasuraman 2 | 7.2 | On Progress | 430000 | 439379.9 | 10% | -2.181% | 2025 | -9379.9
238 | Alamelu & Arvind | 9.9 | Completed | 492000 | 378161.7 | 10% | 23.14% | 2025 | 113838.3
239 | Mr Solai Ayyar | 8.6 | Completed | 562662 | 492142.1 | 10% | 12.53% | 2025 | 70519.9
240 | Ramaniyam Premasaraswathi | 6.6 | Waiting for Net Meter | 320728 | 236014.6 | 10% | 26.41% | 2025 | 84713.4
241 | Mr Pradip Jasiwal | 8.6 | Completed | 555964 | 408683.92 | 10% | 26.49% | 2025 | 147280.08
242 | Mr Mithil & Karan | 16 | Waiting for Net Meter | 800000 | 727147.15 | 10% | 9.107% | 2025 | 72852.85
243 | Radiance Splendour | 161 | Completed | 7369001 | 6523754.331 | 12.5% | 11.47% | 2025 | 845246.669
244 | S&P The Address | 2.4 | Waiting for Net Meter | 125762 | 100353.55 | 10% | 20.2% | 2026 | 25408.45
245 | Ramaniyam Ashok Vihar | 7.7 | Waiting for Net Meter | 372351 | 237418.3 | 10% | 36.24% | 2026 | 134932.7
246 | Mr Deepak Raj | 3.3 | Completed | 205000 | 143312.16 | 10% | 30.09% | 2026 | 61687.84
247 | RCC Austrom Icon | 10 | Completed | 274442 | 225818 | 10% | 17.72% | 2026 | 48624
248 | Ramaniyam Akshayam | 5.5 | Waiting for Net Meter | 290671 | 227657.08 | 10% | 21.68% | 2026 | 63013.92
249 | Ramaniyam Radika | 4.4 | Waiting for Net Meter | 224989 | 167986.3 | 10% | 25.34% | 2026 | 57002.7
250 | M/s Deepa Balaji | 3 | Completed | 210527 | 164705.84 | 10% | 21.76% | 2026 | 45821.16
251 | Mr Pradheep Boopathy | 3 | Completed | 210527 | 162022.24 | 10% | 23.04% | 2026 | 48504.76
252 | Mr Murali | 4.8 | Completed | 347601 | 237187.6 | 10% | 31.76% | 2026 | 110413.4
253 | Ramaniyam Lakshmi | 4.4 | On Progress | 224989 | 148861.06 | 10% | 33.84% | 2026 | 76127.94
254 | Navins Starwood Towers Phase III | 36 | Yet to Start | 1366267 | 1139746.9 | 15% | 16.58% | 2026 | 226520.1
255 | Dra Downtown | 72 | Holding from client | 2665123 | 234402.3 | 10% | 91.2% | 2026 | 2430720.7
256 | M/s Jayanthi | 5 | Yet to Start | 588410 | 283090.3 | 10% | 51.89% | 2026 | 305319.7
257 | Mr Swaminathan | 6 | Yet to Start | 435000 | 312247.3 | 10% | 28.22% | 2026 | 122752.7
258 | M/s Uma Maheshwari | 5 | Yet to Start | 315000 | 256793.4 | 10% | 18.48% | 2026 | 58206.6
259 | M/s V J Saraswathi | 3 | Yet to Start | 206000 | 162393.06 | 10% | 21.17% | 2026 | 43606.94
260 | Mr Sri Kumar | 11 | Waiting for Net Meter | 722634 | 593762.5 | 15% | 17.83% | 2026 | 128871.5
261 | BCPL Anusham | 5 | Yet to Start | 352750 | 233192.6 | 10% | 33.89% | 2026 | 119557.4
262 | BCPL Anusham / Arjun Prasath | 7 | Yet to Start | 495000 | 233192.6 | 10% | 52.89% | 2026 | 261807.4
263 | BCPL Anusham / Dhandapani | 2.3 | Yet to Start | 185851 | 233192.6 | 10% | -25.47% | 2026 | -47341.6
264 | BCPL Anusham / Ramesh | 2.3 | Yet to Start | 185851 | 233192.6 | 10% | -25.47% | 2026 | -47341.6
265 | BCPL Anusham / Sri Bala | 5 | Yet to Start | 352750 | 233192.6 | 10% | 33.89% | 2026 | 119557.4
266 | DRA Infinique | 18 | Yet to Start | 439897 | 234232.3 | 10% | 46.75% | 2026 | 205664.7

## Services
Project Name | Task Name | Assigned date | Assigned to | Status | Due date | Notes | Done by | Credit Amount
GK Shetty tulive Bellevue | to perform general AMC |  | Manikandan | Closed | 2025-12-24 05:30 | Mobile No - 8248637387 , [ 24/12/2025 - General AMC done ] | Manikandan
Rahul Acharya | to give quotation for on grid & off grid systesm |  | Manivel | Open | 2026-04-26 05:30 | [ 9841099169 / Rahul ] / [ 04/12/2025 - general Quote sent to him ] / [ 05/02/2026 - Individual Panel's conditions survey done by Sathyaraj ] / Needs to discuss with him
Theosophical Society | to perform the general water heater service |  | Sathyaraj | Closed | 2025-12-10 05:30 | [ 11/12/2025 - Sathyaraj went and check all the systems and found that all are working within the range ] | Sathyaraj | 0
Ramaniyam Sasta | to complete the Service - MC4 Connector issue |  | Manikandan | Closed | 2025-12-11 05:30 | [ 73583 70333 / Mahesh ] / MC4 Connector Problem | Manikandan & Mohan | 0
GRN Kuyili | to complete the service [ Dinesh / 7299461050 ] |  | Suresh | Closed | 2025-12-29 05:30 | [ 13/12/2025 - Went Site Visit & found that , the inverter's internal board is failure by Suresh ] / [ 15/12/2025 - Complaint registered by Manivel ] / [ 17/12/2025 - Inverter dispatched to Kerala Service Centre by Suresh ] / [ 29/12/2025 - Inverter installed at site & working Normal ] | Manikandan | 0
Mr Govindrajan / Ramaniyam | to send Quote for Water heater tank replacement |  | Manivel | Closed | 2026-02-03 05:30 | [ 72999 27450 / Karthik ] / [ 12/12/2025 -Quote sent to Karthik / Ramaniyam by Manivel ] - They don't want the water heater so asked to remove [ 03/02/2026 - Tank removed and shifted to shiroi by Sathyaraj ] | Sathyaraj | 0
Mr Siva Elango | to check the solar sys's earth |  | Sathyaraj | Closed | 2026-01-12 05:30 | [ 12/01/2026 - Sathyaraj went to site and found that Solar system's earth is connected with the existing system ] | Sathyaraj | 0
Sri Sayee School | complete the Wi Fi dongle re installation |  | Suresh | Closed | 2026-01-12 05:30 | [ 15/12/2025 -Wi Fi re Configuration Completed by Suresh ] / [ 16/12/2025 - Invoice sent via mail ] / -[ 12/01/2026 Payment Receivd ] | Suresh | 4500/-
P S Geetha | to fix water heater , which has been removed from GRN Office |  | Sathyaraj | Closed | 2025-12-16 05:30 | [ Geetha - 98400 19380 - 20 NEHRU NAGAR 2ND STREET ADYAR CHENNAI, Sangam apartments ] / [ Water Heater installed at site and Payment received ] | Sathyaraj | 14750/-
Marutham Rhythm | to check the Service Quote & re share |  | Manivel | Closed | 2026-01-05 05:30 | [ 9884134886 , Kodambakkam ] - Quote Re Shared with them | Manivel | 0
Chettinad Super Speciality Hospital | to done the panel dismantling & re installation |  | Manivel | Closed | 2026-02-18 05:30 | [ 06/01/2026 - Panels removed and stored near the shed area by Sriram contractor 4MP ] / [ 05/02/2026 - Completed the re installation by Sriram Contractor 4 Labours ] / [18/02/2026 - Payment received ] | Manivel | 26255/-
Varsha & Pradeep | to done Water Heater Supply & Installation |  | Manivel | Closed | 2026-01-27 05:30 | [ 07/01/2026 - Water Heater delivered and installed at site ] / [ 13/01/2026 - Invoice sent to them through mail ] / [ 27/01/2026 - Payment Received ] | Sathyaraj | 41418/-
GVG Industries Private ltd | to replace the fault generation meter |  | Manivel | Closed | 2026-03-14 05:30 | [ 14/03/2026 - replacement meter sent to them via courier by Subashri ] | Manivel | 0/-
Navins Office | To Complete the Paid AMC |  | Manikandan | Closed | 2026-01-14 05:30 | Yuvaraj +918148866887 / 14th Jan 2026 - Paid AMC Completed | Manikandan & Mohan
Mr Jeyaseelan | to done Wi Fi Re configurations |  | Manivel | Closed | 2026-01-19 05:30 | Mr Jeyaseelan / 6385144858 | Wi Fi re configurations completed | 0
Lancor TCP Altura | to replace the MCB breaker at the ACDB |  | Anbarasan | Closed | 2026-02-26 05:30 | [ 23/01/2026 - Anbarasan Went site and identified the issue ] / [ 27/01/2026 - Service Quote Sent to Suresh via mail by Manivel ] / [ 03/02/2026 - Breaker replaced by Anbarasan & Mohan , the system is working normal ] / [ 26/02/2026 - Payment sent to Vinod via Gpay ] | Manivel | 4543/-
Mr Sivasankar | to complete Wi Fi Re configurations |  | Manivel | Closed | 2026-01-26 05:30 | Wi Fi Re configuration done | Manivel | 0
Mr Devadoss | service for / off grid inverter not working |  | Manivel | Closed | 2026-01-28 05:30 | [ 27/01/2026 - found that the breaker was dripped and rectified the same by Manikandan ] / [ 28/01/2026 - Again dripped AC breaker and rectified the same by Anbarasan & Manikandan and found that the DC fuse burnt , the same has been replaced by Anbarasan on 29/01/2025 ] | Manikandan | 0
Mr Sankaranarayanan | to complete the structure paint work |  | Manivel | Closed | 2026-02-03 05:30 | [ 03/02/2026 - Structure Paint Work completed by Mr Lourduraj with one labour ] | Manivel | 0/-
Ramaniyam Shyamala | to check the export in the net meter |  | Manikandan | Closed | 2026-02-04 05:30 | [ 04/02/2026 - R Phase export is not working,Now the termination shifted to Y phase, Now the export units is recording ] | Manikandan | 0
Ramaniyam Saranagati | to comple dc cable re route |  | Manivel | Closed | 2026-02-11 05:30 | [ 11/02/2026 - Dc cable re route completed by Manikandan & Mohan ] | Manikandan & Mohan | 0
Mr.Kasinathan | to complete structure painting |  | Manivel | Closed | 2026-02-12 05:30 | [ 12/02/2026 - Structure Painting work completed by Lourduraj with one labour ] | Manivel | 0
Sri Ganapathy Ashram, Phase II | to check the hybrid system feasibility and give note |  | Manivel | Closed | 2026-02-12 05:30 | [ 11/02/2026 - Went Ganapathy ashrama and discussed the feasibility for hybrid system by Manivel & Vivek ] / | Manivel | 0
Ramaniyam Adhri | to check the export units |  | Manivel | Closed | 2026-02-16 05:30 | [ 16/02/2026 - Phase changed in to y , Now the export reading is showing ] | Manikandan | 0
Life Style Param | Service call / to check the all the systems |  | Manivel | Closed | 2026-03-10 05:30 | [ Association Member 9094499900 , 9841473519 Maintenance Person ] / [ 98844 09101 - Gopal Damani / AMC Proposal sent to them on 10/03/2026 ] | Manivel | 0/-
Ramaniyam Anugraha | to check export power |  | Manivel | Closed | 2026-02-23 05:30 | [ 9444081516 / 23/02/2026 - Solar Production is normal, due to high self consumption , there was a no export units, the same has been informed with association people ] | Manivel | 0
Ramakrishna Math | to check the generation |  | Manivel | Closed | 2026-03-04 05:30 | [ 04/03/2026 - Cross checked the system performance , and the system is working within the operating limits ] | Manivel | 0/-
Navin Sanctum | to check the existing on grid system performance |  | Manivel | Closed | 2026-03-10 05:30 | [ 88704 17273 / Vengadanathan / https://maps.app.goo.gl/Ef6wC8qutfT8bJUk6 ] / [ 09/03/2026 - general check up done by Manikandan and found that there was one string problem , the same has been updated to client and asked them change the breaker themselves./ payment received | Manikandan | 1500/-
Mr Sankaranarayanan | to complete the inverter fixining |  | Manikandan | Closed | 2026-03-09 05:30 | Inverter re fixing work done and the system is working within the operating limits. | Manikandan | 0/-
Zebronics | service call |  | Manivel | Closed | 2026-04-25 05:30 | [ 9080341108 Selvam ] / Zebronics Service call | Manivel | 0
Mr Anandan | to done Wi Fi Re configurations |  | Anbarasan | Closed | 2026-03-14 05:30 | Wi Fi re configuration done and checked the existing earth value of the solar systems. | Anbarasan | 0/-
MSM Unit II, Phase I | to replace the fault generation meter |  | Manivel | Closed | 2026-01-06 05:30 | [ 14/03/2026 - replacement meter sent to them via courier by Subashri ] | Manivel | 0/-
GVG Industries Private ltd | to replace the fault inverter |  | Manivel | Closed | 2026-02-28 05:30 | [ 14/03/2026 - Replacement inverter received at gvg factory from Goodwe ] | Manivel | 0/-
Enexio Fill Factory | to complete the FREE AMC |  | Manikandan & Mohan | Closed | 2026-03-14 05:30 | 14th March 2026 - Free AMC done by Manikandan & Mohan | Manikandan & Mohan | 0/-
Mr Ragavan Seapoint Apartment | to complete the service |  | Manikandan | Closed | 2026-03-18 05:30 | 18/03/2026 - Connector Problem and rectified the same / Mr Raghavan / 7358589519 | Manikandan | 500/-
Mr Sairam | to done Wi Fi Re configurations |  | Manikandan | Closed | 2026-03-18 05:30 | Wi Fi Re configuration done | Manikandan | 0/-
Kalakchetra | to complete the structure alteration work |  | Manivel | Closed | 2026-04-25 05:30 | [ 20/03/2026 - Panel & Purlin dismantling work done by Mr Lourduraj with two labour ] , Service Amount Received | Manivel | 23600/-
GRN Ganpat | to check the existing system working conditions |  | Manikandan | Closed | 2026-04-25 05:30 | The system is working within the operating limitts | Manikandan | 500/-
Chettinad Super Speciality Hospital | to done the panel dismantling & re installation @Power House |  | Manivel | Closed | 2026-04-27 05:30 | Solar Panel removal and re installation done at Power House by Mr Sriram Contractor , 27th April service invoice sent to them via mail, Yet to received Payment | Manivel | 21830/-
GRN Sri Mathuram Apartments | to be done general check up |  | Anbarasan | Closed | 2026-04-28 05:30 | Mobile N0 : 9500012418 / [ 27/04/2026 - General Check up done , System's MCB was tripped and rectified the same ] / [ 28/04/2026 - Service amount Received ] | Anbarasan | 1500/-
Enexio Fill Factory | to Complete the FREE AMC |  | Manikandan & Mohan | Closed | 2026-05-20 05:30 | Free AMC done by Mohan & Labour | Mohan | 0/-
AL Sekhar | to visit general service |  | Anbarasan | Closed | 2026-05-16 05:30 | free visit done | Anbarasan | 0/-
GRN Sri Mathuram Apartments | to clean the panels and give demo |  | Sathyaraj | Closed | 2026-05-18 05:30 | Cleaning work done | Sathyaraj | 1500/-
Mr.Rajan Babu | to give panel cleaning demo |  | Sathyaraj | Open | 2026-05-19 05:30 |  |  | 0/-
Mr Rajesh | to complete the service |  | Anbarasan | Closed | 2026-05-22 05:30 | 22nd May - Service call closed, mc4 connector poblem | Anbarasan | 1500/-
Mr Praveen | to replace the dcdb |  | Anbarasan | Closed | 2026-06-02 05:30 | 30th May - Went site and identified that DCDB fault / 2nd June replaced the new DCDB and completed the terminations | Anbarasan | 6292/-

## Plant Monitoring
Project | Brand | Username | Password | Monitoring Link | Created | Actions
GRN Ambili Srinivas | Sungrow | venkatms@rediffmail.com | Solar123 | https://www.isolarcloud.com.hk/#/login | 2025-11-21
Mr Ravi / Tiruvannamalai | Deye | raguramanradha1957@gmail.com | Solar12345 | https://home.solarmanpv.com/login | 2025-12-03
GRN Ambili Srinivas | Sungrow | venkatms@rediffmail.com | Solar123 |  | 2025-11-20
Mr Sukumaran | Deye | divyakalu@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2025-09-18
Mr Rangachari | Deye | anand.Rangachari@gmail.com | vedika!123 | https://home.solarmanpv.com/login | 2025-10-14
Mr Arjun Prasath | Deye | krithiha.arjun@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2025-11-11
Mr Sivasankar | Deye | assikadusiva@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2025-11-14
Mr Sanjay | Havells | swatantrajaiswal30@gmail.com | Solar123 |  | 2025-09-02
Mr. Ramesh Babu | Deye | ramesh.babu@hotmail.com | Solar123 | https://home.solarmanpv.com/login | 2025-10-30
Sri Ganapathy Ashram, Phase II | Deye | ushasankaran1961@gmail.com | Solar123# | https://home.solarmanpv.com/login | 2025-08-18
Shiroi Energy | Sungrow | manivel@shiroienergy.com | shiro@2025 | https://www.isolarcloud.com.hk/#/login | 2025-12-01
Shiroi Energy | Growatt | EEVUWE001 | Solar123 | https://server.growatt.com/login | 2025-12-01
Mr Venkatraman |  | bluetbmvs@gmail.com | Solar123 |  | 2025-12-01
MSM Unit II , Phase II / 400 KWp |  | mrinalstores_msm@yahoo.com | Mrinal@123 | https://www.isolarcloud.com.hk/#/login | 2025-12-01
Mr Felix Johnson | Deye | nancysweetline@gmail.com | Solar@123 | https://home.solarmanpv.com/login
Dr Ramesh / 5 kWp | Deye | dr.rramesh@gmail.com | Solar123 | https://home.solarmanpv.com/login
Shiroi Energy | Deye | manivel@shiroienergy.com | Deye@30# | https://home.solarmanpv.com/login
Mr Anandan | Sungrow | anandananitha@gmail.com | Aarthi@1703 | https://www.isolarcloud.com.hk/#/login
Mr Devadoss / 7 KWp | Deye | sdevadoss1891@gmail.com | Solar123 | https://home.solarmanpv.com/login
Mr Prabakaran / 3.3 KWp | Deye | spn151202@hotmail.com | Solar123 | https://home.solarmanpv.com/login
Mr Chandraprakash | Sungrow | archandraprakash05@gmail.com | Solar123 | https://www.isolarcloud.com.hk/#/login
Enexio Fill Factory | Goodwe | maintenance@enexioindia.com | Solar123
Mr Siva Elango |  | gsivaelango@yahoo.co.in | Solar123
Hindu School Payalwar street | Deye | hssstrip@gmail.com | Solar123 | https://home.solarmanpv.com/login
Mr Arjun Prasath | Deye | krithiha.arjun@gmail.com | Solar123 | https://home.solarmanpv.com/login
Mr Davidson | Deye | sondavid@yahoo.com | Davidson123 | https://home.solarmanpv.com/login
Radiance Flourish | Growatt | Block - C | Fl0ur1sh@2026 | https://server.growatt.com/login
CM Construction | Havells | sarav_cms@yahoo.co.in | Solar12
Mr Rangachari | Deye | anand.Rangachari@gmail.com | Vedika!123 | https://home.solarmanpv.com/login
Mr Ramaswamy | Deye | sai.chandru2017@gmail.com | Saisolar123 | https://home.solarmanpv.com/login
Mr.Kasinathan | Growatt | kasinathan | Solar123 | https://server.growatt.com/login | 2025-12-06
Sri Sayee School | Growatt | srisayee | Solar123 | https://server.growatt.com/login | 2025-12-15
Mr Jeyakumar |  | rjkr123@gmail.com | Solar123 |  | 2025-12-24
Mr Nitin | Sungrow | nitinkadambari@yahoo.co.in | Solar123 | https://www.isolarcloud.com.hk/#/login | 2026-01-04
Mr Ashok | Fronious | panchapakesanashok1@gmail.com | Ashokp@Solar123 / Solar123 |  | 2025-12-22
Swarnalatha | Deye | vsl_boss@yahoo.co.in | Solar123 | https://home.solarmanpv.com/login | 2026-01-10
Mr Jeyaseelan |  | jneumarin@gmail.com | Solar123 |  | 2025-06-20
Arihanth Nahar | Deye | m.arihantnahar@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2025-11-08
Mr Sundar |  | hariram1700@ymail.com | Solar123 |  | 2026-01-23
Oriental Hydraulics Private Limited | Goodwe | mail2@shiori.com | Solar123 |  | 2026-01-27
Hindu School Adyar | Fimer | Hinduschool | Solar@123 | https://www.auroravision.net/ums/v1/loginPage?redirectUrl=https:%2F%2Fwww.auroravision.net%2Fhome%2F | 2025-11-04
Mr.Karthikeyan / CM Constructions |  | jkarthik.nr@gmail.com | Solar123 |  | 2026-02-10
M/s Latha Ganesh | Deye | latsgana@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2026-02-19
Ceebros Boulevard | Growatt | Cbfoasolar | Solar123 | https://server.growatt.com/login | 2024-04-17
Solver Minds / 8 KWp | Goodwe | infraadmin@solverminds.com | Solver123 |  | 2026-02-20
Solver Minds / 81 KWp | Fimer | Solverminds | Solar@123 | https://www.auroravision.net/ums/v1/loginPage?redirectUrl=https:%2F%2Fwww.auroravision.net%2Fhome%2F | 2026-02-20
GVG Industries Private Ltd | Goodwe | Gvgindustries@gmail.com | Admin@123 |  | 2026-03-02
Lancor Hiranmayi |  | ganasa@hotmail.com | Solar123 |  | 2026-03-03
Mr Koildhass | Deye | kdoss00@yahoo.com | Solar@123 | https://home.solarmanpv.com/login | 2026-03-05
Mr Sairam | Deye | vupputursairam@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2025-05-30
Alamelu & Arvind | Polycab | Alusolar | Hamra@466 | https://pv.polycabmonitoring.com/dist/#/login/index | 2026-03-25
Mr Sivasankar Home | Deye | sankar_hema@rediffmail.com | Solar123 | https://home.solarmanpv.com/login | 2029-03-28
Mr Solai Ayyar | Deye | indraayyar10@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2026-04-02
Mr Sridhar Rajan | Deye | Sridharrajan1989@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2026-04-18
Mr Deepka Raj | Polycab | Deepakraj | Solar123 | https://pv.polycabmonitoring.com/dist/#/login/index | 2026-04-24
M/s Deepa Balaji | Polycab | Balajissolar | Solar@123 | https://pv.polycabmonitoring.com/dist/#/login/index | 2026-05-01
Mr Pradheep Boopathy | Polycab | Pradheepsolar | Solar@123 | https://pv.polycabmonitoring.com/dist/#/login/index | 2026-05-01
Mr Shanmugam | Deye | spshanmu@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2026-05-01
Krishnaveni | Growatt | Jegan moorthy | Solar123 | https://server.growatt.com/login | 2025-12-03
Mr Murali | Deye | kmurali020@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2026-05-09
Chettinad Hospital | Growatt | CHETTINADRHC | Solar123 | https://server.growatt.com/login | 2026-05-11
Mr Muthu | Flin Energy | Muthu | Solar123 | http://power-datacenter.com/cmc/login_system.html | 2026-05-12
A/A2 - Mrs Nithiya Ramachandran | Deye | Nithyaram | Solar@123 | https://home.solarmanpv.com/login
A/A3 - Mrs Asumitha | Deye | Ashmitha | Solar@123 | https://home.solarmanpv.com/login
A/A4 - Mr Venkatramani | Deye | Venkatramani | Solar@123 | https://home.solarmanpv.com/login
A/A5 & A/A6 - Mr Ravi | Deye | Ravianju | Solar@123 | https://home.solarmanpv.com/login
B/A1 - Mrs Jayashree | Deye | Jayashri | Solar@123 | https://home.solarmanpv.com/login
B/A2 - Mr Ramachandran | Deye | Ckram99 | Solar@123 | https://home.solarmanpv.com/login
B/A3 - Mr Nitin | Deye | NitinkumarB3 | Solar@123 | https://home.solarmanpv.com/login
B/A4 - Mr Manoj | Deye | BManoj | Solar@123 | https://home.solarmanpv.com/login
B/A5 - Mr Gowtham | Deye | Gautham | Solar@123 | https://home.solarmanpv.com/login
B/A6 - Mr Unnikrishnan | Deye | Unnivalliyil | Solar@123 | https://home.solarmanpv.com/login
C/A1 - Mr Jayaraman | Deye | JJayabarthi | Solar@123 | https://home.solarmanpv.com/login
C/A3 - Mrs Shree Latha | Deye |  |  | https://home.solarmanpv.com/login
C/A5 - Mrs Geeth Priya | Deye | Geethapriya | Solar@123 | https://home.solarmanpv.com/login
D/A1 - Mr Sudharsan | Deye | Sutharsan | Solar@123 | https://home.solarmanpv.com/login
D/A3 - | Deye | DA3 | Solar@123 | https://home.solarmanpv.com/login
D/A4 - Mr Shajee | Deye | Phshajee | Solar@123 | https://home.solarmanpv.com/login
E/A1 - Mr Vanagiri | Deye | EA1vanagiri | Solar123 | https://home.solarmanpv.com/login
E/A2 - Mr Sekar | Deye | Shekar | TN37LP8383 | https://home.solarmanpv.com/login
E/A3 - Mr Ramachandran | Deye | Ramachandrank | Solar@123 | https://home.solarmanpv.com/login
E/A4 - Mr Sundar Rajan | Deye | Sundarrajan | Solar@123 | https://home.solarmanpv.com/login
E/A5 - Mrs Rajalakshmi | Deye | Rajalakshmi | Solar@123 | https://home.solarmanpv.com/login
E/A6 - Mrs Gomathi | Deye | EA6Gomathi | Solar@123 | https://home.solarmanpv.com/login
F/A1 - Mrs Sripriya | Deye | kanmani | Solar@123 | https://home.solarmanpv.com/login
F/A2 - Mr Meenakshi Sundaram | Deye | Seyon | Solar@123 | https://home.solarmanpv.com/login
F/A3 - Mrs Anuradha Ganeshan | Deye | Anuradhaganesh | Solar123 | https://home.solarmanpv.com/login
F/A6 - Mrs Vidiya | Deye | Aksmaniyan | Solar@123 | https://home.solarmanpv.com/login
F/A7 - Mr Mohan | Deye | kMohan | Solar@123 | https://home.solarmanpv.com/login
F/A8 - Mrs Sridevi Ashokan | Deye | Sridevi ashok | Solar@123 | https://home.solarmanpv.com/login
F/A9 - Mr Selvarajan | Deye | Selvarajan | Solar@123 | https://home.solarmanpv.com/login
G/A1 - Mr Ramasamy Annamalai | Deye | GA1 | Solar@123 | https://home.solarmanpv.com/login
G/A2 - Mr Arun | Deye | Arunnithya | Solar@123 | https://home.solarmanpv.com/login
H/A2 - Mr Bhadri | Deye | HA2 | Solar@123 | https://home.solarmanpv.com/login
H/A3 - Mr Ramasamy | Deye | Ramasamy | Solar@123 | https://home.solarmanpv.com/login
H/A6 - Mr Durai Murugan | Deye | Nduraimurugan | Solar@123 | https://home.solarmanpv.com/login
H/A8 - Mr Selvakumar | Deye | Sselvakumar | Solar@123 | https://home.solarmanpv.com/login
H/A9 - Mrs Latha Ragu | Deye | Raghuvamsham | Solar@123 | https://home.solarmanpv.com/login
H/A10 - Mr Baskaran | Deye | Dhanamuthu | Solar@123 | https://home.solarmanpv.com/login
H/A11 - Mr Kumar | Deye | K.kumar | Solar@123 | https://home.solarmanpv.com/login
J/A1 - Mr Veerasekar | Deye | Veerasekar | Solar@123 | https://home.solarmanpv.com/login
J/A2 - Mr Ashok | Deye | Ashokja2 | Solar@123 | https://home.solarmanpv.com/login
J/A3 - Mrs Nivetha | Deye | Nivedhasivakumar | Solar@123 | https://home.solarmanpv.com/login
J/A4 - Mr Nagasubrish | Deye | Nagasabarish | Solar@123 | https://home.solarmanpv.com/login
J/A5 - Mr Naresh | Deye | Nareshjoghee | Solar@123 | https://home.solarmanpv.com/login
J/A6 - | Deye | Geethabalu | Solar@123 | https://home.solarmanpv.com/login
J/A7 - | Deye | SPrabhakar | Solar@123 | https://home.solarmanpv.com/login
J/A8 - Mr Sudha Srivilasan | Deye | Sudhasri | Solar@123 | https://home.solarmanpv.com/login
J/A9 - Mr Suresh | Deye | Smitra | Solar@123 | https://home.solarmanpv.com/login
A L Sekhar | Growatt | AL Sekhar | Solar123 | https://server.growatt.com/login | 2026-05-16
Mr.Rajan Babu | Growatt | rajanbabut | Solar123 | https://server.growatt.com/login | 2025-11-22
Mr.Sriram Pallikaranai | Deye | balasfinearts@gmail.com | Solar@123 | https://home.solarmanpv.com/login | 2025-10-05
Mr Raja grn gopal street | Deye | Jayanthi.raja1964@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2026-06-05
vanai Panache | Deye | vinaismav@gmail.com | Solar@123
Varun - Besant nagar ( 4.3kw ) | Deye | varunp@gmail.com | Solar@123
AM RAJA - Besant nagar ( 3.2 KW ) | Growatt | Amraja | Solar123
Shridhar - Tambaram ( 6 kw ) | Deye | shridhar1953@gmail.com | Solar123
Chemfab Alkalis SS_110 KWp | Fimer | Chemfabalkalis | Solar@123
Chemfab Alkalis SS_55 KWp | Fimer | Shiroienergy | Solar@123
Chemfab Alkalis SS_8.7 KWp | Fimer | Shiroienergy | Solar@123
Chemfab Alkalis DP_11.5 KWp | Fimer | Shiroienergy | Solar@123
Chemfab Alkalis SP_11.5 KWp | Fimer | Shiroienergy | Solar@123
Chemfab Alkalis RO_23 KWp | Fimer | Shiroienergy | Solar@123
Schangalaya_25 KWp | Fimer | Shiroienergy | Solar@123
Schakaralaya_50 KWp | Fimer | Shiroienergy | Solar@123
Mountmeru _108KWp | Fimer | Mountmeru_Solar | Solar@123
Mountmeru _103 KWp | Fimer | Mountmeru_Solar | Solar@123
Harsha_2 KWp | Fimer | harsha123 | Solar@123
Baskar_2.5 KWp | Fimer | Bossshyam | Solar2019@
Ashok_4 KWp | Fronius solar web | mail@shiroienergy.com | Shiroienergy@04
Ashok_2.5 KWp | Havells | shravan@shiroienergy.com | Solar123
Mugundamani_3 KWp | Fronious | mail@shiroienergy.com | Shiroienergy@04
GRN Poes Garden_4 KWp | Fronious | mail@shiroienergy.com | Shiroienergy@04
Siddharth_1 KWp | Fimer | Siddharth | Solar@123
Sriram_4 KWp | Fimer | Sriramsv | Solar@123
Sri Sayee School_16 KWp | Growatt | srisayee | vivekananda
Sri Sayee School_1 KWp | Growatt | SSVV | ssvv2019
Dhayanada School_7.8 KWp | Fimer | Dayananda | Solar@123
Chemfab sricity _110 KWp | Fimer | Shiroienergy | Solar@123
Chemfab sricity _115 KWp | Fimer | Shiroienergy | Solar@123
Edison School _48 KWp | Fimer | Edisonschool | Generator@123
Madurai SLCS College_88 KWp | Fimer | slcscollege | Admin@123
Chemin Enviro System_45KWp | Fimer | CESZLDS45KW | Ces@7788
Chemin Enviro System_2KWp | Fimer | CESZLDS2KW | Ces@7788
GGN School _15 KWp | Fimer | Ggnschool | Solar@123
Hindu School_50 KWp | Fimer | Hinduschool | Solar@123
Solverminds_81 KWp | Fimer | Solverminds | Solar@123
Solverminds_8 KWp | Goodwee | infraadmin@solverminds.com | Solver123
RKM1_20 KWp | Goodwee | manivel@shiroienergy.com | Solar@123
RKM2_20 KWp | Goodwee | manivel@shiroienergy.com | Solar@123
RKM3_5 KWp | Goodwee |  | Solar@123
GVN_Hospital_60KWp | Fimer | Gvnhospital | Solar@123
Mrinal_mills_507Kwp_Inverter_1(125Kwp) | Goodwee | mrinalstores_msm@yahoo.com | Mrinal@123
Mrinal_mills_507Kwp_Inverter_2(125Kwp) | Goodwee | mrinalstores_msm@yahoo.com | Mrinal@123
Mrinal_mills_507Kwp_Inverter_3(125Kwp) | Goodwee | mrinalstores_msm@yahoo.com | Mrinal@123
Mrinal_mills_507Kwp_Inverter_4(132Kwp) | Goodwee | mrinalstores_msm@yahoo.com | Mrinal@123
RWD Lemongras_20Kwp | Goodwee | Maintenance.lemongraz@gmail.com | Goodwe2018
Soori Besant nagar_5Kwp | Polycab | shravan@shiroienergy.com | Admin123
Chemittiya_Palakad_5Kwp | Growatt | chemittiya | Solar@123
Kumaraguru_5kw | Growatt | Kumarguru | admin123
Chandru_5kw | Growatt | Chandru | admin123
Metal forms-SPK110Kw-Inv-1(165Kw) | Goodwee | Mail2@shiroienergy.com | Solar123
Metal forms-SPK55Kw-Inv-2(165Kw) | Goodwee | Mail2@shiroienergy.com | Solar123
Metal forms-Redhills-110Kw-Inv-1(330Kw) | Goodwee | mail2@shiori.com | Solar123
Metal forms-Redhills-110Kw-Inv-2(330Kw) | Goodwee | mail2@shiori.com | Solar123
Metal forms-Redhills-110Kw-Inv-3(330Kw) | Goodwee | mail2@shiori.com | Solar123
SVA syntex pvt.ltd-126.5Kw-Inv-1(253Kw) | Goodwee | svafactory@gmail.com | Goodwe2018
SVA syntex pvt.ltd-126.5Kw-Inv-2(253Kw | Goodwee | svafactory@gmail.com | Goodwe2018
GVG Industries pvt.ltd-123Kw-Inv-1(370Kw) | Goodwee | gvgindustries@gmail.com | Admin@123
GVG Industries pvt.ltd-123Kw-Inv-2(370Kw) | Goodwee | gvgindustries@gmail.com | Admin@123
GVG Industries pvt.ltd-123Kw-Inv-3(370Kw) | Goodwee | gvgindustries@gmail.com | Admin@123
SVPB Spinners pvt.ltd-123.2Kw-Inv-1(248Kw) | Goodwee | gvgindustries@gmail.com | Admin@123
SVPB Spinners pvt.ltd-125.4Kw-Inv-2(248Kw) | Goodwee | gvgindustries@gmail.com | Admin@123
Sri krishna Sweets Factory | Goodwee | tech@srikrishnasweets.net | Solar@123 | https://www.semsportal.com/home/login | 2026-06-09
Premier Tiruvanandapuram-27KW | Goodwee | accounts@premieroffice.in | Solar@123
Shankar narayanan-Plaza-5Kw | Growatt | gtshankar@gmail.com | Pass@1234
RKM-17Kw-(32KW)-Inv-1 | Growatt | RKMmylapore | Solar@123
RKM-15Kw-(32KW)-Inv-2 | Growatt | RKMmylapore | Solar@123
Nebu Olympia Panache (8KW) | Goodwee | achayan@gmail.com | neenu555
Karthick ECR (9.6KW) | Deye | chrome6boy@gmail.com | Solar@123
Suresh Panache (5KW) | Deye | ssuresh2480@gmail.com | Solar@123
Praveen (4KW) | Deye | prajugops@gmail.com | Solar@123
Praveen (2KW) | Deye | prajugops@gmail.com | Solar@123
Ambatore Rotary Hospital (50KW) | Growatt | arhsolar | Solar123
Lavanya Shankar (5 KW) | Deye | shravan@shiroienergy.com | Solar123
Shiroi Energy LLP | Goodwe | manivel@shiroienergy.com | Solar@123 |  | 2026-06-06
M/s V J Saraswathi | Deye | vigneshsambasivam46@gmail.com | Solar123 | https://home.solarmanpv.com/login | 2026-06-06

## Activities
Date | Project Name | Stage | Done By | Description | SE Manpower | Out Source Manpower | Contractor Manpower | Notes
2026-06-05 05:30 | DRA Trinity | Site Visit | Manivel | Discussed with them, they have asked to finish the wiring work at site by 15th June | 1 |  | 0 | Nil
2026-06-08 05:30 | BCPL Anusham | Site Survey | Manikandan & Manikandan A | Electrical materials delivered to site | 2 |  |  | Nil
2026-06-08 05:30 | DRA Infinique | Site Visit | Manivel | Site Visit done and discussed with project manager about delivery status and structure , design finalization | 1
2026-06-08 05:30 | DRA Trinity | Installation | Manikandan & Manikandan A & Mohan | Earth Pit Delivered to site and installed the same | 3 |  | 0 | Nil
2026-06-06 05:30 | DRA Trinity | Installation | Manivel | Earth Pit Excavation done for two numbers in depth of 2 meter | 1 | 2 | 0 | Nil
2026-06-08 05:30 | Ramaniyam Rangavilasam | Commissioning | Manikandan | System commissioning has been done | 1 | 0 | 0 | Nil
2026-06-08 05:30 | Radiance Splendour | Service | Manivel & Anbarasan | Site Visit done to check the existing system termination points | 1 | 0 | 0 | Nil
2026-06-08 05:30 | DRA Trinity | Procurement | Manivel | Bill of items created and shared with procurement team | 0 | 0 | 0 | Nil
2026-06-08 05:30 | Newry Adora | Procurement | Manivel | Bill of Item created and shared with procuremnet team | 0 | 0 | 0 | Nil
2026-06-06 05:30 | Newry Adora | Site Visit | Manikandan | Site Visit done and discussed routing, bill of items | 1 | 0 | 0 | Nil
2026-06-09 05:30 | Newry Adora | Procurement | Manivel | Received Quote for Structure from green field and order placed for the same | 0 | 0 | 0 | Nil
2026-05-08 05:30 | Shoba Silks Pvt Ltd | Commissioning | Manivel | 8th May 2026 - Drawing Approval received | 0
2026-05-11 05:30 | Shoba Silks Pvt Ltd | Commissioning | Manivel | 11th May 2026 - Covering letter for inspection sent to client to get signature
2026-05-15 05:30 | Shoba Silks Pvt Ltd | Commissioning | Manivel | 15th May 2026 - Received Signed letter from Shoba Silks
2026-06-09 05:30 | Shoba Silks Pvt Ltd | Follow Ups | Manivel | Soke with dhanalakshi about CEIG Inspection at Shoba Silks, he confirmed that will happen on 10th 2 PM | 0 | 0 | 0 | Nil
2026-06-09 05:30 | M/s Jayanthi | Procurement | Manivel | Structure order placed with green field / GI low Raise | 0 | 0 | 0 | Nil
2026-06-09 05:30 | Sri krishna Sweets Factory | Commissioning | Anbarasan | Net Meter installed at site and system commissioning has been done | 1 | 0 | 0 | Yet to complete the Aggregator unit configurations
2026-05-31 05:30 | Navins Starwood Towers Phase III | Installation | Manivel | Structure Materials delivered to site and unloaded at store room by Sriram Contractor | 1 | 0 | 2 | Nil
2026-05-15 05:30 | Navins Starwood Towers Phase III | Design | Manivel | Design sent to them via Wats App to get confirmation | 1 | 0 | 0 | Nil
2026-05-16 05:30 | Navins Starwood Towers Phase III | Design | Manivel | Revised design sent to them | 1 | 0 | 0 | Nil
2026-05-27 05:30 | Navins Starwood Towers Phase III | Design | Manivel | Got design confirmation | 1 | 0 | 0 | Nil
2026-05-28 05:30 | Navins Starwood Towers Phase III | Procurement | Manivel | Structure order placed with Sriram Contractor | 1 | 0 | 0 | Nil
2026-06-09 05:30 | Navins Starwood Towers Phase III | Installation | Mohankumar | 58 Nos / Vikram 620 Wp Solar Panels delivered to site and unloaded by Sriram contractor, Shifted to 5th floor, structure materials shifted to terrace from store room. | 1 |  | 5 | Nil
2026-06-09 05:30 | Sri krishna Sweets Factory | Follow Ups | Manivel | Follow up with MRT AD to complete the Net Meter installation & Subashri Engineering to complete the aggregator units | 1 | 0 | 0 | Nil